## Cover
ICS2 Known Error List
Version: | 3.20
Date: | 2025-12-15
Updated: | Incidents and PM/KE's with functional impact were added. The timelines of the existing KEL entries, incidents (resulting in PM/KE's) and RfC's updated where relevant.

## KEL EO
ICS2 Known Error List EO
ID | Date | Impacted artefact |  |  | Identified error |  | Solution | Impact |  |  | Planned IT implementation |  | Implemented in artefact |  | Implementation in conformance (the indicated timing can vary and will be updated in case of a change) | Implementation in production (the indicated timing can vary and will be updated in case of a change) | Software release version | Priority | Impact
|  | Title | Date | Version | Message/R&C/BR | Description |  | SD | MS | Trade | Date | Release | Date | Version
1 | 2019-08-26 | 5.2. CFSS-IEs-(2019-04-26)-v1.12 | 2019-04-26 | 1.12 | IE3R03 IE4R03 | In the 'HRCM screening response' messages the 'Authorised person' (HRCM Screening Response/Authorised Person) is a Mandatory (M) element, however, there could be no 'Authorised person'. | IE3R03/HRCM Screening Response/Authorised Person - 'Optional' (O) IE4R03/HRCM Screening Response/Authorised Person - 'Optional' (O) | Y | Y | Y |  | 1 |  | 1.13 | N/A | In production |  | Low | Medium
5 | 2019-08-26 | 5.2. CFSS-IEs-(2019-04-26)-v1.12 | 2019-04-26 | 1.12 | IE3N99 IE4N99 | In the Error notification messages (IE3N99, IE4N99) the element “LRN” is changed to “Functional reference number”. | IE3N99/LRN is renamed into IE3N99/Functional reference number. IE4N99/LRN is renamed into IE4N99/Functional reference number. | Y | Y | Y |  | 1 |  | 1.13 | N/A | In production |  | Low | Low
7 | 2019-08-26 | 5.2. CFSS-IEs-(2019-04-26)-v1.12 | 2019-04-26 | 1.12 | IE3A32, IE3F32, IE4A32, IE4F32, IE4N05, IE4Q01, IE4Q02, IE4R05 | The code list for the currency (CL352) is currently not indicated in the generated messages. | CL352 added to the attributes: IE3A32, IE3F32, IE4A32, IE4F32 Consignment (Master level)/Consignment (House level)/Total amount invoiced/Currency Consignment (Master level)/Consignment (House level)/Additions and deductions/Amount/Currency Consignment (Master level)/Consignment (House level)/Goods item/Item amount invoiced/Currency IE4N05 Related PLACI/Consignment (Master level)/Consignment (House level)/Additions and deductions/Amount/Currency Related ENS/Consignment (Master level)/Consignment (House level)/Additions and deductions/Amount/Currency IE4Q01/IE4Q02/IE4R05 Related ENS/Consignment (Master level)/Consignment (House level)/Additions and deductions/Amount/Currency | Y | Y | Y |  | 1 |  | 1.13 | N/A | In production |  | Medium | Medium
19 | 2019-09-26 | CD3-ICS2-HTI-Interface Control Document-SfA-v1.90 |  | 1.90 | AS4 protocol | EOs may have an EORI number fro a given MS but register the authorisation certificate in another. For those cases the validation of the certificate registration must be redirected to other MS than the one in the EORI code. | For the cases defined an additional optional data element is added in the technical header of AS4 messages. PartyID will be EORI@System@MS" |  |  | Y |  | 1 |  |  | N/A | In production |  | Medium | Medium
20 | 2019-10-14 | 5.2. CFSS-IEs-(2019-08-26)-v1.13 | 2019-08-26 | 1.13 | IE3F32 IE4F32 IE3A32 IE4A32 | Gross mass' at goods item level is mandatory in IExx32 messages, however the declarant cannot know exact gross mass of each goods item in the parcel. For this reason the weight is only mandatory on House consingment level and is declared as 'Total gross mass'. | Change: IE3F32/Consignment (Master level)/Consignment (House level)/Goods Item/Weight - Optional (O) IE4F32/Consignment (Master level)/Consignment (House level)/Goods Item/Weight - Optional (O) IE3A32/Consignment (Master level)/Consignment (House level)/Goods Item/Weight - Optional (O) IE4A32/Consignment (Master level)/Consignment (House level)/Goods Item/Weight - Optional (O) | Y | Y | Y |  | 1 |  | 1.14 | N/A | In production |  | Medium | Medium
21 | 2019-10-14 | 5.2. CFSS-IEs-(2019-08-26)-v1.13 | 2019-08-26 | 1.13 | IE3F32 IE4F32 IE3A32 IE4A32 | In the air pre-loading messages that contain the 'HRCM screening results' class the 'Authorised person' (HRCM Screening Results/Authorised Person) is a Mandatory (M) element, however, there could be no 'Authorised person'. | IE3F32/HRCM Screening Results/Authorised Person - 'Optional' (O) IE4F32/HRCM Screening Results/Authorised Person - 'Optional' (O) IE3A32/HRCM Screening Results/Authorised Person - 'Optional' (O) IE4A32/HRCM Screening Results/Authorised Person - 'Optional' (O) | Y | Y | Y |  | 1 |  | 1.14 | N/A | In production |  | Medium | Medium
25 | 2019-10-14 | 5.2. CFSS-IEs-(2019-08-26)-v1.13 | 2019-08-26 | 1.13 | All messages | Date and time format in CFSS and CTSS is not aligned. | The format of date and time attributes YYYY-MM-DDThh:mm:ssZ | Y | Y | Y |  | 1 |  | 1.14 | N/A | In production |  | High | High
27 | 2019-10-14 | 5.2. CFSS-IEs-(2019-08-26)-v1.13 | 2019-08-26 | 1.13 | IE3Q03 IE4Q05 | Referral request details/Transport document (House level)/Type' and Referral request details/Transport document (House level)/Reference number' should be mandatory. If the Class 'Transport document (House level)' is used the attributes shall be mandatory. | IE3Q03/Referral request details/Transport document (House level)/Type - Mandatory (M) IE3Q03/Referral request details/Transport document (House level)/Reference number - Mandatory (M) IE4Q05/Referral request details/Transport document (House level)/Type - Mandatory (M) IE4Q05/Referral request details/Transport document (House level)/Reference number - Mandatory (M) | Y | Y | Y |  | 1 |  | 1.14 | N/A | In production |  | Medium | Medium
30 | 2019-11-12 | 5.2. CFSS-IEs-(2019-08-26)-v1.13 | 2019-08-26 | 1.13 | IExFxx IExAxx | Code list for 'Commodity code' is missing | IExFxx/Consignment (Master level)/Goods item/Commodity/Commodity code - CL706 IExAxx/Consignment (Master level)/Goods item/Commodity/Commodity code - CL706 IExFxx/Consignment (Master level)/Consignment (House level)/Goods item/Commodity/Commodity code - CL706 IExAxx/Consignment (Master level)/Consignment (House level)/Goods item/Commodity/Commodity code - CL706 | Y | Y | Y |  | 1 |  | 1.14 | N/A | In production |  | Medium | Medium
35 | 2019-12-20 | 5. CFSS-IEs-(2019-11-29)-v1.14 | 2019-11-29 | 1.14 | IE3N08 IE3N09 IE4N09 IE4N11 | Transport document (Master level) is manadatory in the messages, however, in Release 1 for postal ENSs and express ENS in Release 1 and 2 this data attribute does not exist. | IE3N08/Transport document (Master level) - Optional (O) IE3N09/Transport document (Master level) - Optional (O) IE4N09/Transport document (Master level) - Optional (O) IE4N11/Transport document (Master level) - Optional (O) | Y | Y | Y |  | 1 |  | 1.15 | N/A | In production |  | Medium | Medium
40 | 2020-03-31 | ICS2-CFSS-CL-(2020-03-31)-v1.22 | 2020-03-31 | 1.22 | CL723 Functional error code | Code 96 with code list value "Incorrect entity reference" to cover the cases when a valid value is provided but the value does not correspond to the relevant entity - for example, a valid MRN is provided but MRN of an Arrival notification/ENS Filing whereas an MRN of an ENS was expected. Code 97 with code list value "Not found" to cover the cases when certain entity is not found. | CL723 96 "Incorrect entity reference" 97 "Not found" | Y | Y | Y |  | 2 |  | 1.22 | N/A | In production |  | Medium | Medium
44 | 2020-04-15 | 5. ICS2-CFSS-IE-(2020-03-31)-v1.22 | 2020-03-31 | 1.22 | IExx23 IExx24 IExx32 | The "Commodity code" is Optional for the following ENS Filing types - F23, F24 and F32. | "Commodity code" in the following messages to be modifed from C(onditional) to O(ptional) with C3025 to be removed. IE3A23/Consignment (Master level)/Consignment (House level)/Goods item/Commodity/Commodity code C -> O IE3F23/Consignment (Master level)/Consignment (House level)/Goods item/Commodity/Commodity code C -> O IE4A23/Consignment (Master level)/Consignment (House level)/Goods item/Commodity/Commodity code C -> O IE4F23/Consignment (Master level)/Consignment (House level)/Goods item/Commodity/Commodity code C -> O IE3A24/Consignment (Master level)/Consignment (House level)/Goods item/Commodity/Commodity code C -> O IE3F24/Consignment (Master level)/Consignment (House level)/Goods item/Commodity/Commodity code C -> O IE4A24/Consignment (Master level)/Consignment (House level)/Goods item/Commodity/Commodity code C -> O IE4F24/Consignment (Master level)/Consignment (House level)/Goods item/Commodity/Commodity code C -> O IE3A32/Consignment (Master level)/Consignment (House level)/Goods item/Commodity/Commodity code C -> O IE3F32/Consignment (Master level)/Consignment (House level)/Goods item/Commodity/Commodity code C -> O IE4A32/Consignment (Master level)/Consignment (House level)/Goods item/Commodity/Commodity code C -> O IE4F32/Consignment (Master level)/Consignment (House level)/Goods item/Commodity/Commodity code C -> O | Y | Y | Y |  | 2 |  | 1.23 | N/A | In production |  | Medium | Medium
46 | 2020-05-15 | ICS2-CFSS-R&C-(2019-11-29)-v1.12 | 2019-11-29 | 1.12 | R3023 | R3023 needs to be modified to specify explicitly that, in case it is available, the information should be provided at CONSIGNMENT level only if applicable to all Goods items. Otherwise, it should be provided per Goods item. | R3023 to be modified to: This class should be provided, if available, either at CONSIGNMENT level or CONSIGNMENT/GOODS ITEM level. Where the same information is applicable to all Goods items in the same Consignment, it should be provided at CONSIGNMENT level only. | Y | Y | Y |  | 1 |  | 1.13 | N/A | In production |  | Low | Medium
47 | 2020-05-15 | ICS2-CFSS-R&C-(2020-03-31)-v1.22 | 2020-03-31 | 1.22 | R3023 R3031 | R3023 and R3031 need to be modified to specify explicitly that, in case it is available, the information should be provided at CONSIGNMENT level only if applicable to all Goods items. Otherwise, it should be provided per Goods item. | R3023 to be modified to: This class should be provided, if available, either at CONSIGNMENT level or CONSIGNMENT/GOODS ITEM level. Where the same information is applicable to all Goods items in the same Consignment, it should be provided at CONSIGNMENT level only. R3031 to be modified to: This class should be provided, if available, either at CONSIGNMENT level or CONSIGNMENT (HOUSE LEVEL)/GOODS ITEM level. Where the same information is applicable to all Goods items in the same Consignment, it should be provided at CONSIGNMENT level only. | Y | Y | Y |  | 2 |  | 1.23 | N/A | In production |  | Low | Medium
50 | 2020-11-16 | HTI ICD | 2020-09-15 | 2.70 |  | Based on initial pre-conformance testing with selected Economic Operators we have identified some points of concern that requires us to perform some minimal changes to the “ICS2 Harmonized Trader Interface - Interface Control Document” with respect to the @type attribute of two data elements. | 4.2.2.1 eb:PartyId The content of this element is a string value that provides an identification for the given party. The namespace for content values of this element is specified by the eb:PartyId@type attribute. […] This implies that the domain namespaces will have a structure as follows: urn:oasis:names:tc:ebcore:partyid-type:unregistered:<catalog-name>:<schema-name> where catalog-name will be 'eu-customs' and schema-name will be one of the two values 'authority' or 'EORI'. In the authority namespace urn:oasis:names:tc:ebcore:partyid-type:unregistered:eu-customs:authority each STI/NTI will be assigned an identifier providing it a PartyId. The partyId of the ICS2 STI is sti-taxud, the partyId of the NTI will be nti-<iso 3166-1 Alpha2 code>. […] 4.2.3.1 eb:AgreementRef The eb:AgreementRef element is mandatory in ICS2 TI exchanges and serves the additional purpose of identifying a version of the Trader Interface common specifications. The first version is EU-ICS2-TI-V1.0. As per ebMS 3 specification ([R07]), the eb: AgreementRef element will be qualified by a @type attribute with a value of “ics2-interface-version” (empty string), to allow such values in the content of the data element. […] | Y | N | Y |  | 1 |  | 2.80 | N/A | In production |  | Medium | Medium
53 | 2020-10-27 | 5. ICS2-CFSS-IE-(2020-07-17)-v1.23 | 2020-07-17 | 1.23 | IE3N08 Control notification | There is a misalignment between IE4N09 and IE3N08 - the "Receptacle" on House level is not applicable to IE3N08 since it is not provided in IE4N09. | The following class to be removed: Control/Control subject/Consignment (Master level)/Consignment (House level)/Receptacle. | Y |  | Y |  | 2 |  | 1.24 | N/A | In production |  | Medium | Medium
65 | 2021-01-08 | ICS2-CFSS-CL-(2020-03-31)-v1.13 | 2020-03-31 | 1.13 | CL724 HRCM Screening Method | Code List value ZZZ 'Only one HRCM screening method required' is missing. | Value will be addedd into CL document. CL724 ZZZ "Only one HRCM screening method required" | Y | Y | Y |  | 1 |  | 1.1.13 | N/A | In production |  | Medium | Medium
66 | 2021-01-08 | ICS2-CFSS-CL-(2020-07-17)-v1.23 | 2020-07-17 | 1.23 | CL724 HRCM Screening Method | Code List value ZZZ 'Only one HRCM screening method required' is missing. | Value will be addedd into CL document. CL724 ZZZ "Only one HRCM screening method required" | Y | Y | Y |  | 2 |  | 1.24 | N/A | In production |  | Medium | Medium
78 | 2021-02-12 | 5. ICS2-CFSS-IE-(2020-07-17)-v1.23 7. ICS2-CFSS-CL-(2020-07-17)-v1.23 | 07-17-2020 | 1.23 | CL144 UNLOCODE | CL144 to be replaced by CL244 | In the code list document CL144 UNLOCODE to be replaced by CL244 UNLOCODE. All messages where CL144 is used to be updated with CL244. | Y | Y | Y |  | 2 |  | 1.24 | N/A | In production |  | High | High
85 | 2021-04-07 | 5. ICS2-HTI-IE-(2021-03-19)-v1.24 | 2021-03-19 | 1.24 | IE3A32, IE3F32, IE3A43, IE3F43, | The format of the "Role" (CL756) of "Additional fiscal references" should be changed from "a..3" to "an..3". | "IExx32/Consignment (Master level)/Consignment (House level)/Additional fiscal references/Role" an..3 "IExx43/Consignment (Master level)/Consignment (House level)/Additional fiscal references/Role" an..3 | Y | Y | Y |  | 2 |  | 1.25 | N/A | In production |  | High | High
87 | 2021-04-14 | 5. ICS2-HTI-IE-(2021-03-19)-v1.24 | 2021-03-19 | 1.24 | All ENS filings IExAxx and IExFxx | The identification number of the "Representative" is an EORI number (R3005 is missing). | R3005 to be added to ENS Filings/Representative/Identification number. | Y |  | Y |  | 2 |  | 1.25 | N/A | In production |  | High | High
88 | 2021-04-14 | 5. ICS2-HTI-IE-(2021-03-19)-v1.24 | 2021-03-19 | 1.24 | IE3N08, IE3R02, IE3R03, IE3N06, IE3N08 IExx10, IExx11, IExx12, IExx13, IExx14, IExx15, IExx20, IExx21, IExx22, IExx26, IExx27, IExx28, IExx29, IExx31, IExx33 | An EORI number is expected to be used for "Notify party", "Person notifying the arrival", "Carrier", "Declarant" and "Representative" (R3005 is missing), | R3005 to be added to the "Notify party/Identification number" in IE3N08 and the following ENS filings: IExx10, IExx11, IExx12, IExx13, IExx14, IExx15, IExx20, IExx21, IExx22, IExx26, IExx27, IExx28, IExx29, IExx31, IExx33. R3005 to be added to the "Representative/Identification number" for IE3R02, IE3R03. R3005 to be added to the "Declarant/Identification number" for IE3R02, IE3R03. R3005 to be added to the "Person notifying the arrival/Identification number" for IE3N06, IE3N08. | Y | Y | Y |  | 2 |  | 1.25 | N/A | In production |  | High | High
89 | 2021-04-14 | 5. ICS2-HTI-IE-(2021-03-19)-v1.24 | 2021-03-19 | 1.24 | IExx15 | R3051 to be removed. | IExx15/Consignment (Master level)/Consignment (House level)/Additional supply chain actor/Role R3051 (R3051 to be removed). | Y |  | Y |  | 2 |  | 1.25 | N/A | In production |  | High | High
91 | 2021-04-14 | 7. ICS2-HTI-CL-(2019-11-29)-v1.13 | 2019-22-29 | 1.13 | CL723 Functional error code | A new code list value needs to be introduced. | CL723 101 "No new goods items or house consignments can be added via an ENS filing amendment" | Y |  | Y |  | 1 |  | 1.14 | N/A | In production |  | Medium | Medium
93 | 2021-04-14 | 7. ICS2-HTI-CL-(2021-03-19)-v1.24 | 2021-03-19 | 1.24 | CL723 Functional error code | A new code list value needs to be introduced. | CL723 101 "No new goods items or house consignments can be added via an ENS filing amendment" | Y |  | Y |  | 2 |  | 1.25 | N/A | In production |  | Medium | Medium
100 | 2021-04-22 | 7. ICS2-HTI-CL-(2021-03-19)-v1.24 | 2021-03-19 | 1.24 | CL717 Country code (ICS2 MS) | GB to be removed from CL717 and XI (Northern Ireland) to be added to CL717. | CL717 Country code (ICS2 MS) GB Great Britain XI Northern Ireland | Y | Y | Y |  | 2 |  | 1.25 | N/A | In production |  | High | Medium
101 | 2021-04-22 | 7. ICS2-HTI-CL-(2019-11-29)-v1.13 | 2019-11-29 | 1.13 | CL717 Country code (ICS2 MS) | GB to be removed from CL717 and XI (Northern Ireland) to be added to CL717. | CL717 Country code (ICS2 MS) GB Great Britain XI Northern Ireland | Y | Y | Y |  | 1 |  | 1.14 | N/A | In production |  | High | Medium
105 | 2021-05-18 | 5. ICS2-HTI-IE-(2021-04-23)-v1.25 | 2021-04-23 | 1.25 | IE3R02, IE4R02 | There is a discrepancy between the XSD format and the note of the "Referral request reference" in IE3R02 and IE4R02. | The XSD's format of the "Additional information response/Referral request reference" format to be modified from an..35 to an..17. | Y | Y | Y |  | 2 |  | 2.00 | N/A | In production |  | Low | Medium
106 | 2021-05-18 | 5. ICS2-HTI-IE-(2021-04-30)-v1.30 | 2021-04-30 | 1.30 | IE3R02, IE4R02 | There is a discrepancy between the XSD format and the note of the "Referral request reference" in IE3R02 and IE4R02. | The XSD's format of the "Additional information response/Referral request reference" format to be modified from an..35 to an..17. | Y | Y | Y |  | 3 |  | 2.00 | N/A | In production |  | Low | Medium
109 | 2021-06-03 | 6. ICS2-HTI-R&C-(2019-11-29)-v1.12 | 2019-11-29 | 1.12 | R3052 | The 'Transport document (House level)' must be unique within the submitted ENS filing. | R3052 Each ‘Transport document (House level)’ must be unique throughout the ENS filing. | Y |  | Y |  | 1 |  | 1.13 | N/A | In production |  | High | Medium
110 | 2021-06-03 | 5. ICS2-HTI-IE-(2020-01-08)-v1.15 | 2020-01-08 | 1.15 | IExx43 | R3052 to be attached to 'Transport document (House level)'. | IExx43/Consignment (Master level)/Consignment (House level)/Transport document (House level) R3052. | Y |  | Y |  | 1 |  | 1.16 | N/A | In production |  | High | Medium
111 | 2021-06-03 | 6. ICS2-HTI-R&C-(2021-03-19)-v1.24 | 2021-03-19 | 1.24 | R3052 | The 'Transport document (House level)' must be unique within the submitted ENS filing. | R3052 Each ‘Transport document (House level)’ must be unique throughout the ENS filing. | Y |  | Y |  | 2 |  | 2.00 | N/A | In production |  | High | Medium
112 | 2021-06-03 | 5. ICS2-HTI-IE-(2021-04-23)-v1.25 | 2021-04-23 | 1.25 | IExx43 | R3052 to be attached to 'Transport document (House level)'. | IExx43/Consignment (Master level)/Consignment (House level)/Transport document (House level) R3052. | Y |  | Y |  | 2 |  | 2.00 | N/A | In production |  | High | Medium
113 | 2021-06-03 | 6. ICS2-HTI-R&C-(2021-04-30)-v1.30 | 2021-04-30 | 1.30 | R3052 | The 'Transport document (House level)' must be unique within the submitted ENS filing. | R3052 Each ‘Transport document (House level)’ must be unique throughout the ENS filing. | Y |  | Y |  | 3 |  | 2.00 | N/A | In production |  | High | Medium
114 | 2021-06-03 | 5. ICS2-HTI-IE-(2021-04-30)-v1.30 | 2021-04-30 | 1.30 | IExx43 | R3052 to be attached to 'Transport document (House level)'. | IExx43/Consignment (Master level)/Consignment (House level)/Transport document (House level) R3052. | Y |  | Y |  | 3 |  | 2.00 | N/A | In production |  | High | Medium
115 | 2021-06-21 | 6. ICS2-HTI-R&C-(2021-03-19)-v1.24 | 2021-03-19 | 1.24 | R3053 | The date and time of arrival cannot be earlier than the date and time of departure. | R3053 The 'Estimated date and time of arrival' cannot be earlier than the 'Actual date and time of departure' or 'Estimated date and time of departure'. | Y |  | Y |  | 2 |  | 2.00 | N/A | In production |  | Medium | Medium
116 | 2021-06-21 | 6. ICS2-HTI-R&C-(2021-04-30)-v1.30 | 2021-04-30 | 1.30 | R3053 | The date and time of arrival cannot be earlier than the date and time of departure. | R3053 The 'Estimated date and time of arrival' cannot be earlier than the 'Actual date and time of departure' or 'Estimated date and time of departure'. | Y |  | Y |  | 3 |  | 2.00 | N/A | In production |  | Medium | Medium
117 | 2021-06-21 | 5. ICS2-HTI-IE-(2021-04-23)-v1.25 | 2021-04-23 | 1.25 | IExx20, IExx21, IExx27, IExx28, IExx29, IExx30, IExx31, IExx42 | R3053 to be attached to 'Estimated date and time of arrival', 'Actual date and time of departure' and 'Estimated date and time of departure'. | IExx42 Estimated date and time of arrival Estimated date and time of departure Actual date and time of departure IExx20, IExx28 Estimated date and time of arrival Estimated date and time of departure IExx21, IExx27, IExx29, IExx30, IExx31 Estimated date and time of arrival Actual date and time of departure | Y |  | Y |  | 2 |  | 2.00 | N/A | In production |  | Medium | Medium
118 | 2021-06-21 | 5. ICS2-HTI-IE-(2021-04-30)-v1.30 | 2021-04-30 | 1.30 | IExx10, IExx11, IExx12, IExx13, IExx20, IExx21, IExx27, IExx28, IExx29, IExx30, IExx31, IExx34, IExx40, IExx41, IExx42, IExx45, IExx50, IExx51 | R3053 to be attached to 'Estimated date and time of arrival', 'Actual date and time of departure' and 'Estimated date and time of departure'. | IExx10, IExx11, IExx12, IExx13, IExx34, IExx40, IExx41, IExx42, IExx45, IExx50, IExx51 Estimated date and time of arrival Estimated date and time of departure Actual date and time of departure IExx20, IExx28 Estimated date and time of arrival Estimated date and time of departure IExx21, IExx27, IExx29, IExx30, IExx31 Estimated date and time of arrival Actual date and time of departure | Y |  | Y |  | 3 |  | 2.00 | N/A | In production |  | Medium | Medium
119 | 2021-06-21 | 7. ICS2-HTI-CL-(2021-04-23)-v1.25 | 2021-04-23 | 1.25 | CL723 Functional error code | A new code list value needs to be introduced. | CL723 Functional error code 103 The date and time of arrival cannot be earlier than the date and time of departure. | Y |  | Y |  | 2 |  | 2.00 | N/A | In production |  | Medium | Medium
120 | 2021-06-21 | 7. ICS2-HTI-CL-(2021-04-30)-v1.30 | 2021-04-30 | 1.30 | CL723 Functional error code | A new code list value needs to be introduced. | CL723 Functional error code 103 The date and time of arrival cannot be earlier than the date and time of departure. | Y |  | Y |  | 3 |  | 2.00 | N/A | In production |  | Medium | Medium
126 | 2021-07-05 | 6. ICS2-HTI-R&C-(2021-04-30)-v1.30 | 2021-04-30 | 1.30 | R3006 | Addition of a pattern to be checked. | R3006 When 'COMMUNICATION/Type' is 'TE' the 'COMMUNICATION/Identifier' has to have an international phone number format as defined in the ITU-T recommendation E.123 (02/2001). The format must be compliant with the pattern "^\\+(?:[0-9] ?){6,14}[0-9]$”. | Y | Y | Y |  | 3 |  | 2.00 | N/A | In production |  | Medium | Medium
127 | 2021-07-05 | 5. ICS2-HTI-IE-(2021-04-30)-v1.30 | 2021-04-30 | 1.30 | IExx30 | R3022 ''COUNTRIES OF ROUTING OF CONSIGNMENT' must contain countries of 'PLACE OF ACCEPTANCE' and 'PLACE OF DELIVERY'.' to be removed from "Consignment (Master level)/Consignment (House level)/Countries of routing of consignment". | IExx30/Consignment (Master level)/Consignment (House level)/Countries of routing of consignment R3022 | Y | Y | Y |  | 3 |  | 2.00 | N/A | In production |  | Medium | Medium
130 | 2021-07-30 | 5. ICS2-HTI-IE-(2021-04-23)-v1.25 | 2021-04-23 | 1.25 | IExx30, IExx34 | R3023 to be removed from "Additional supply chain actor" at "Consignment (Master level)" as there is no "Goods item" level. | IExx30/Consignment (Master level)/Additional supply chain actor R3023 IExx34/Consignment (Master level)/Additional supply chain actor R3023 | Y |  | Y |  | 2 and 3 |  | 2.00 | N/A | In production |  | Low | Medium
131 | 2021-07-30 | 5. ICS2-HTI-IE-(2021-04-23)-v1.25 | 2021-04-23 | 1.25 | IExx25 | R3023 to be removed from "Additional information". | IExx25/Consignment (Master level)/Consignment (House level)/Additional information R3023 | Y |  | Y |  | 2 |  | 2.00 | N/A | In production |  | Low | Medium
132 | 2021-07-30 | 5. ICS2-HTI-IE-(2021-04-23)-v1.25 | 2021-04-23 | 1.25 | IExx23 IExx24 IExx25 | R3001 to be added to the "Additional information" | IExx25/Consignment (Master level)/Consignment (House level)/Additional information R3001 IExx24/Consignment (Master level)/Consignment (House level)Additional information R3001 IExx24/Consignment (Master level)/Consignment (House level)/Goods item/Additional information R3001 IExx23/Consignment (Master level)/Consignment (House level)Additional information R3001 IExx23/Consignment (Master level)/Consignment (House level)/Goods item/Additional information R3001 | Y |  | Y |  | 2 |  | 2.00 | N/A | In production |  | Medium | Medium
133 | 2021-07-30 | 5. ICS2-HTI-IE-(2021-04-23)-v1.25 | 2021-04-23 | 1.25 | IE3R02, IE4R02 | MIME data element is missing from the HRCM Screening results/Binary attachment | IE3R02/HRCM Screening results/Binary attachment/MIME M 1..1 to be added. IE4R02/HRCM Screening results/Binary attachment/MIME O 0..1 to be added | Y | Y | Y |  | 2 |  | 2.00 | N/A | In production |  | Medium | Medium
134 | 2021-07-30 | 5. ICS2-HTI-IE-(2021-04-30)-v1.30 | 2021-04-30 | 1.30 | IExx10 IExx11 | R3021 is not applicable to the "Container indicator" and should be removed. | IExx10/Consignment (Master level)/Consignment (House level)/Container indicator R3021 IExx11/Consignment (Master level)/Container indicator R3021 | Y |  | Y |  | 3 |  | 2.00 | N/A | In production |  | Medium | Medium
149 | 2021-07-30 | 5. ICS2-HTI-IE-(2021-04-23)-v1.25 | 2021-04-23 | 1.25 | IExx30, IExx43 | When there is no "Type of packages" there is no need for the "Packaging" to be with miltiplicity upper limit more than 1. | IExx30, IExx43 "Consignment (Master level)/Consignment (House level)/Goods item/Packaging" from 1..99 to 1..1. | Y |  | Y |  | 2 |  | 2.00 | N/A | In production |  | Low | Medium
150 | 2021-07-30 | 5. ICS2-HTI-IE-(2021-04-23)-v1.25 | 2021-04-23 | 1.25 | IExx42 | The "Communication" cardinality of the "Representative" needs to be aligned to the other ENS filings. | IExx42 "Representative/Communication" 1..1 to 1..9. | Y |  | Y |  | 2 |  | 2.00 | N/A | In production |  | Low | Medium
151 | 2021-07-30 | 5. ICS2-HTI-IE-(2021-04-30)-v1.30 | 2021-04-30 | 1.30 | IExx13 | The "Seal" is on House consignment level, not on Master consignment level. The attached condition is C3015 and should be corrected to C3017. | IExx13 "Consignment (Master level)/Consignment (House level)/Transport equipment/Seal" C3015 to C3017. | Y |  | Y |  | 3 |  | 2.00 | N/A | In production |  | Low | Medium
163 | 2021-09-23 | 5. ICS2-HTI-IE-(2021-07-30)-v2.00 | 2021-07-30 | 2.00 | IExx31 IExx33 | The "Reference number/UCR" on house consignment level has to be mandatory in order to allow the correct association to the relevant PLACI. | "IExx31/Consignment (Master level)/Consignment (House level)/Reference number/UCR" to be changed from O 0..1 to M 1..1. "IExx33/Consignment (Master level)/Consignment (House level)/Reference number/UCR" to be changed from O 0..1 to M 1..1. | Y |  | Y |  | 2 and 3 |  | 2.01 | N/A | In production |  | Medium | Medium
165 | 2021-10-11 | 5. ICS2-HTI-IE-(2021-07-30)-v2.00 | 2021-07-30 | 2.00 | IExx15 | The "Identification number" of the Supplementary declarant in F15 should be mandatory, not optional. | "IExx15/Consignment (Master level)/Consignment (House level)/Supplementary declarant/Identification number" from O 0..1 to M 1..1. | Y |  | Y |  | 3 |  | 2.01 | N/A | In production |  | Medium | Medium
166 | 2021-10-11 | 5. ICS2-HTI-IE-(2021-07-30)-v2.00 | 2021-07-30 | 2.00 | IExx17 | The "Identification number" of the Representative in F17 should be mandatory, not optional. | "IExx17/Representative/Identification number" from O 0..1 to M 1..1. | Y |  | Y |  | 3 |  | 2.01 | N/A | In production |  | Medium | Medium
167 | 2021-10-11 | 5. ICS2-HTI-IE-(2021-07-30)-v2.00 | 2021-07-30 | 2.00 | IExx23 IExx24 IExx25 | R3033 to be added to the "Representative/Identification number". | "IExx23/Representative/Identification number" R3033 "IExx24/Representative/Identification number" R3033 "IExx25/Representative/Identification number" R3033 | Y |  | Y |  | 2 and 3 |  | 2.01 | N/A | In production |  | Medium | Medium
186 | 2021-11-12 | 7. ICS2-HTI-CL-(2021-07-30)-v2.00 | 2021-07-30 | 2.00 | CL723 Functional error code | A new error code to be added in case the economic operator tries to amend a non-amendable data element. | CL723 Functional error codes 104 Element cannot be amended | Y |  | Y |  | 2 and 3 |  | 2.0.1 | N/A | In production |  | Medium | Medium
191 | 2021-12-21 | 5. ICS2-HTI-IE-(2021-07-30)-v2.00 | 2021-07-30 | 2.00 | IExx13 | The information to be provided for the transport equipment needs to be aligned to UCC/Annex B. | IExx13 "Consignment (Master level)/Consignment (House level)/Transport equipment" "Container size and type" from M 1..1 to O 0..1 "Container packed status" from M 1..1 to O 0..1 "Container supplier type" from M 1..1 to O 0..1 | Y |  | Y |  | 3 |  | 2.01 | N/A | In production |  | Medium | Medium
192 | 2021-12-21 | 5. ICS2-HTI-IE-(2021-07-30)-v2.00 | 2021-07-30 | 2.00 | IExx45 | The "Previous MRN" is missing from the "Split consignment". | IExx45 "Split consignment/Previous MRN" C 0..1 C3001 to be added. | Y |  | Y |  | 3 |  | 2.01 | N/A | In production |  | Medium | Medium
193 | 2021-12-21 | 5. ICS2-HTI-IE-(2021-07-30)-v2.00 | 2021-07-30 | 2.00 | IExx17 | F17 to be corrected. | IExx17 IE3F17/LRN from O 0..1 to M 1..1. IE3A17/LRN to be removed. "Consignment (Master level)/Consignment (House level)" cardinality to be modified from 1..99999 to 1..1. | Y |  | Y |  | 3 |  | 2.01 | N/A | In production |  | Medium | Medium
194 | 2021-12-21 | 5. ICS2-HTI-IE-(2021-07-30)-v2.00 | 2021-07-30 | 2.00 | IExx51 | There is no "Type of identification" and "Identification number" for the "Active border transport means" for F51. | IExx51 "Active border transport means/Type of identification" to be removed. "Active border transport means/Identification number" to be removed. | Y |  | Y |  | 3 |  | 2.01 | N/A | In production |  | Medium | Medium
195 | 2021-12-21 | 5. ICS2-HTI-IE-(2021-07-30)-v2.00 | 2021-07-30 | 2.00 | IExx50, IExx51 | The "Seal" information is missing from "Consignment (House level)". | IExx50, IExx51 "Consignment (Master level)/Consignment (House level)/Transport equipment/Number of seals" O 0..1 added. "Consignment (Master level)/Consignment (House level)/Transport equipment/Seal" C 0..9 C3017 added. | Y |  | Y |  | 3 |  | 2.01 | N/A | In production |  | Medium | Medium
196 | 2021-12-21 | 5. ICS2-HTI-IE-(2021-07-30)-v2.00 | 2021-07-30 | 2.00 | IExx40, IExx41 | There should be no "Split consignment" for F40 and F41. | IExx40, IExx41 "Split consignment" removed. | Y |  | Y |  | 3 |  | 2.01 | N/A | In production |  | Medium | Medium
199 | 2021-12-21 | 5. ICS2-HTI-IE-(2021-07-30)-v2.00 | 2021-07-30 | 2.00 | IExx14, IExx15 | As per UCC/Annex B there is "Passive border transport means" for F14 and F15 in "Consignment (House level)". | IExx14, IExx15 "Passive border transport means" added at "Consignment (Master level)/Consignment (House level)". | Y |  | Y |  | 3 |  | 2.01 | N/A | In production |  | Medium | Medium
203 | 2022-02-15 | 5. ICS2-HTI-IE-(2021-07-30)-v2.00 | 2021-07-30 | 2.00 | R3023 | R3023 to be removed. | R3023 "This class should be provided, if available, either at CONSIGNMENT level or CONSIGNMENT/GOODS ITEM level. Where the same information is applicable to all Goods items in the same Consignment, it should be provided at CONSIGNMENT level only." to be removed. | Y |  | Y |  | 2 and 3 |  | 2.01 | N/A | In production |  | Medium | High
204 | 2022-02-15 | 5. ICS2-HTI-IE-(2022-12-22)-v2.01 | 2021-12-22 | 2.01 | R3023 in IExx10, IExx11, IExx12, IExx13, IExx14, IExx15, IExx16, IExx17, IExx20, IExx21, IExx22, IExx23, IExx24, IExx26, IExx27, IExx28, IExx29, IExx30, IExx31, IExx32, IExx33, IExx34, IExx43, IExx50, IExx51 | R3023 to be removed from all ENS filing types. | R3023 to be removed from these data classes - "Additional information", "Additional supply chain actor", "Passive border transport means", "Supporting documents", "Transport equipment" - in the listed ENS filing types. | Y |  | Y |  | 2 and 3 |  | 2.02 | N/A | In production |  | High | High
205 | 2022-02-15 | 5. ICS2-HTI-IE-(2022-12-22)-v2.01 | 2021-12-22 | 2.01 | IE3R04 | There is a discrepancy of the length of the LRN data element in the XSD and the Excel/RTF. | IE3R04/LRN to be modified from an..35 to an..22 in the XSD. | Y | Y | Y |  | 2 and 3 |  | 2.02 | N/A | In production |  | Medium | Medium
214 | 2022-02-28 | 7. ICS2-HTI-CL-(2021-07-30)-v2.00 | 2021-07-30 | 2.00 | CL721 ENS entity type (Subset) | PLACI house consignment to be removed from the code list CL721 ENS entity type (subset) for the economic operators. | CL721 ENS entity type (Subset) CPL PLACI house consignment | Y |  | Y |  | 2 and 3 |  | 2.01 | N/A | In production |  | Low | Low
215 | 2022-03-21 | 5. ICS2-HTI-IE-(2021-12-22)-v2.01 | 2021-12-22 | 2.01 | IExx30, IExx32 | The multiplicity of the "Goods item" is not sufficient for the economic operators. It should be increased. | IExx30, IExx32 "Consignment (Master level)/Consignment (House level)/Goods item" from 1..99 to 1..9999. | Y |  | Y |  | 2 and 3 |  | 2.02 | N/A | In production |  | Medium | Medium
216 | 2022-03-21 | 5. ICS2-HTI-IE-(2021-12-22)-v2.01 | 2021-12-22 | 2.01 | IExx34 | The multiplicity of the "Goods item" is not sufficient for the economic operators. It should be increased. | IExx34 "Consignment (Master level)/Consignment (House level)/Goods item" from 1..99 to 1..9999. | Y |  | Y |  | 3 |  | 2.02 | N/A | In production |  | Medium | Medium
219 | 2022-03-23 | 5. ICS2-HTI-IE-(2021-12-22)-v2.01 | 2021-12-22 | 2.01 | IE3Fxx IE4Fxx IE3Axx IE4Axx | R3001 to be removed from all ENS filings. | R3001 to be removed from "Additional informaion" in all ENS filings. | Y |  | Y |  | 2 and 3 |  | 2.02 | N/A | In production |  | High | High
220 | 2022-03-23 | 6. ICS2-HTI-R&C-(2021-07-30)-v2.00 | 2021-07-30 | 2.00 | R3001 | The rule R3001 to be removed. | R3001 "When 'ADDITIONAL INFORMATION' class is used, either 'ADDITIONAL INFORMATION/Code' or 'ADDITIONAL INFORMATION/Text' has to be used." to be removed. | Y |  | Y |  | 2 and 3 |  | 2.02 | N/A | In production |  | High | High
226 | 2022-04-07 | 5. ICS2-HTI-IE-(2021-12-22)-v2.01 | 2021-12-22 | 2.01 | IE3R01 IE4R01 | The Specific circumstance indicator needs to be included in the ENS Registration response to the EO. | The data element "Specific circumstance indicator" an3 CL742 to be added to the ENS Registration response message as 1..1 M. | Y |  | Y |  | 2 and 3 |  | 2.02 | N/A | In production |  | High | High
234 | 2022-06-24 | 5. ICS2-HTI-IE-(2022-05-04)-v2.02 | 2022-05-04 | 2.02 | IE3N07 IE4N08 | The "Transport document (Master level)" in the "IE3N07/IE4N08 House consignment in incorrect state notification" message cannot be mandatory. | IE3N07/IE4N08 House consignment in incorrect state notification "Transport document (Master level)" from 1..1 M to 0..1 O. | Y | Y | Y |  | 2 and 3 |  | 2.03 | N/A | In production |  | Medium | Medium
240 | 2022-08-24 | 5. ICS2-HTI-IE-(2022-05-04)-v2.02 | 2022-05-04 | 2.02 | IE3A50 IE3A51 | The communication class is missing for the Carrier in IE3A50 and IE3A51. | IE3A50/Consignment (Master level)/Carrier/Communication O 0..9 to be added. IE3A50/Consignment (Master level)/Carrier/Communication O 0..9 to be added. | Y |  | Y |  | 3 |  | 2.03 | In conformance | In production | 3.1.0.0 | Low | Medium
243 | 2022-09-29 | 5. ICS2-HTI-IE-(2022-05-04)-v2.02 | 2022-05-04 | 2.02 | IExx10 | C3013 to be replaced by C3014 since there is no containers on master level, but only on house level. | "IE3A10/Consignment (Master level)/Consignment (House level)/Transport equipment" C3013 -> C3014 "IE3F10/Consignment (Master level)/Consignment (House level)/Transport equipment" C3013 -> C3014 "IE4A10/Consignment (Master level)/Consignment (House level)/Transport equipment" C3013 -> C3014 "IE4F10/Consignment (Master level)/Consignment (House level)/Transport equipment" C3013 -> C3014 | Y |  | Y |  | 3 |  | 2.03 | In conformance | In production | 3.1.0.0 | Low | Medium
245 | 2022-09-29 | 5. ICS2-HTI-IE-(2022-05-04)-v2.02 | 2022-05-04 | 2.02 | IExx50, IExx51 | C3025 to be replaced by C3054. | "IE3A50/Consignment (Master level)/Consignment (House level)/Goods item/Commodity/Commodity code" C3025 -> C3048 "IE3F50/Consignment (Master level)/Consignment (House level)/Goods item/Commodity/Commodity code" C3025 -> C3048 "IE4A50/Consignment (Master level)/Consignment (House level)/Goods item/Commodity/Commodity code" C3025 -> C3048 "IE4F50/Consignment (Master level)/Consignment (House level)/Goods item/Commodity/Commodity code" C3025 -> C3048 "IE3A51/Consignment (Master level)/Consignment (House level)/Goods item/Commodity/Commodity code" C3025 -> C3048 "IE3F51/Consignment (Master level)/Consignment (House level)/Goods item/Commodity/Commodity code" C3025 -> C3048 "IE4A51/Consignment (Master level)/Consignment (House level)/Goods item/Commodity/Commodity code" C3025 -> C3048 "IE4A51/Consignment (Master level)/Consignment (House level)/Goods item/Commodity/Commodity code" C3025 -> C3048 | Y |  | Y |  | 3 |  | 2.03 | In conformance | In production | 3.1.0.0 | Medium | Medium
246 | 2022-09-29 | 6. ICS2-HTI-R&C-(2022-05-23)-v2.01 | 2022-05-23 | 2.01 | R3031 | R3031 to be removed. | R3031 "This class should be provided, if available, either at CONSIGNMENT level or CONSIGNMENT (HOUSE LEVEL)/GOODS ITEM level. Where the same information is applicable to all Goods items in the same Consignment, it should be provided at CONSIGNMENT level only." to be removed. | Y |  | Y |  | 3 |  | 2.02 | In conformance | In production | 3.1.0.0 | Medium | Medium
247 | 2022-09-29 | 5. ICS2-HTI-IE-(2022-05-04)-v2.02 | 2022-05-04 | 2.02 | IExx10 | R3031 to be removed from all IExx10 data elements. | "IExx10/Consignment (Master level)/Consignment (House level)/Supporting documents" R3031 "IExx10/Consignment (Master level)/Consignment (House level)/Additional supply chain actor" R3031 "IExx10/Consignment (Master level)/Consignment (House level)/Goods item/Supporting documents" R3031 "IExx10/Consignment (Master level)/Consignment (House level)/Goods item/Additional information" R3031 "IExx10/Consignment (Master level)/Consignment (House level)/Goods item/Additional supply chain actor" R3031 "IExx10/Consignment (Master level)/Consignment (House level)/Goods item/Transport equipment" R3031 "IExx10/Consignment (Master level)/Consignment (House level)/Transport equipment" R3031 | Y |  | Y |  | 3 |  | 2.03 | In conformance | In production | 3.1.0.0 | Medium | Medium
248 | 2022-10-18 | 6. ICS2-HTI-R&C-(2022-05-23)-v2.01 | 2022-05-23 | 2.01 | R3018 | The case of "XI" must be included as a special case since the country in the routing countries for the active means of transport will not be "XI" but "GB" ("XI" is not a country as per the ISO country codes). | R3018 In the sequence of 'ACTIVE BORDER TRANSPORT MEANS/Countries of routing of means of transport' the first country that is an EU Member State must be the country of the 'CUSTOMS OFFICE OF FIRST ENTRY' or in case the COFE is "XI" then "GB" must be listed in the 'ACTIVE BORDER TRANSPORT MEANS/Countries of routing of means of transport' before any ICS2 country. | Y |  | Y |  | 2 and 3 |  | 2.02 | N/A | In production |  | High | Medium
259 | 2023-01-30 | ICS2-HTI-BPML4 Process Description-(2021-07-30)-v2.00 | 2021-07-30 | 2.00 | T-01-01 – Perform syntactical and semantical validation | A footnote to be added to the description of the task regarding the allowed characters encodings. | T-01-01 – Perform syntactical and semantical validation The below footnote to be added to the text “…Cyrillic, Latin or Greek…”. "Footnote: Characters from the following UnicodeBlocks are allowed: basic_latin, latin_1_supplement, latin_extended_a, latin_extended_b, greek, cyrillic, cyrillic_supplementary, phonetic_extensions, phonetic_extensions_supplement, latin_extended_additional, greek_extended, general_punctuation, superscripts_and_subscripts, currency_symbols, number_forms, cyrillic_extended_a" | Y |  | Y |  | 2 and 3 |  | 2.01 | N/A | In production |  | High | High
260 | 2023-02-22 | 7. ICS2-HTI-CL-(2022-05-23)-v2.01 | 2022-05-23 | 2.01 | CL703 Additional information type | The code list CL703 Additional information type should be added to the code lists for the economic operators. | CL703 Additional information type R1 RFI request R2 RFI response R4 RFS response Remark: For the economic operators only R1, R2 and R4 are applicable values. | Y |  | Y |  | 2 and 3 |  | 2.02 | N/A | In production |  | Low | Low
261 | 2023-02-22 | 7. ICS2-HTI-CL-(2022-05-23)-v2.01 | 2022-05-23 | 2.01 | CL244 UNLOCODE | To align to the names used in CS/RD2 the code list part of the CFSS have to be updated with the names used in CS/RD2. | CL244 UNLOCODE -> UnlocodeExtended | Y | Y | Y |  | 2 and 3 |  | 2.02 | N/A | In production |  | Low | Low
262 | 2023-03-08 | 5. ICS2-HTI-IE-(2022-05-04)-v2.02 | 2022-05-04 | 2.02 | IExx50, IExx51 | The "Container indicator" data element on master level to be removed. | IExx50, IExx51 "Consignment (Master level)/Container indicator" to be removed. | Y |  | Y |  | 3 |  | 2.03 | In conformance | In production | 3.1.0.0 | Medium | Medium
263 | 2023-03-10 | 5. ICS2-HTI-IE-(2022-05-04)-v2.02 | 2022-05-04 | 2.02 | IExx34 | The "Estimated date and time of arrival" must be mandatory. | IExx34 "Active border transport means/Estimated date and time of arrival" from O 0..1 to M 1..1. | Y |  | Y |  | 3 |  | 2.03 | In conformance | In production | 3.1.0.0 | Medium | Medium
271 | 2023-07-19 | 7. ICS2-HTI-CL-(2022-05-23)-v2.01 | 2022-05-23 | 2.01 | CL723 Functional error code | The code list value of code 101 to be modified. | CL723 Functional error code 101 "It is not possible to add new goods items or house consignments via an ENS filing amendment" to be modified to "It is not possible to remove or to add goods items or house consignments via an ENS filing amendment" | Y |  | Y |  | 2 and 3 |  | 2.02 | N/A | In production | 3.0.0.0 | Low | Low
273 | 2023-07-20 | 5. ICS2-HTI-IE-(2022-05-04)-v2.02 | 2022-05-04 | 2.02 | IExA34, IExA40, IExA41, IExA45 | R3024 is missing from the amendments for the listed ENS filing types. | R3024 to be attached to the following data classes/elements: IExA34 Specific circumstance indicator Representative Representative/Identification number Active border transport means/Mode of transport Consignment (Master level)/Carrier/Identification number Consignment (Master level)/Consignment (House level)/Goods item/Goods item number Consignment (Master level)/Consignment (House level)/Transport document (House level)/Reference number Declarant/Identification number Customs office of first entry/Reference number IExA40 Specific circumstance indicator Representative Representative/Identification number Active border transport means/Mode of transport Consignment (Master level)/Carrier/Identification number Consignment (Master level)/Transport document (Master level)/Reference number Declarant/Identification number Customs office of first entry/Reference number IExA41 Specific circumstance indicator Representative Representative/Identification number Active border transport means/Mode of transport Consignment (Master level)/Carrier/Identification number Consignment (Master level)/Transport document (Master level)/Reference number Declarant/Identification number Customs office of first entry/Reference number IExA45 Specific circumstance indicator Representative Representative/Identification number Active border transport means/Mode of transport Consignment (Master level)/Carrier/Identification number Consignment (Master level)/Transport document (Master level)/Reference number Declarant/Identification number Customs office of first entry/Reference number | Y |  | Y |  | 3 |  | 2.03 | In conformance | In production | 3.1.0.0 | Medium | High
280 | 2023-09-07 | 6. ICS2-HTI-R&C-(2022-05-23)-v2.01.docx | 2022-05-23 | 2.01 | R3018 | If the current wording of R3018 is kept then the master ENS filings submitting "ACTIVE BORDER TRANSPORT MEANS/Countries of routing of means of transport" for transporting EU goods crossing UK and coming back to EU or re-entry cases indicating the complete routing of the active border transport means of transport (the country of the first COFE and the country of the next COFE) will be rejected. | R3018 Current wording: "In the sequence of 'ACTIVE BORDER TRANSPORT MEANS/Countries of routing of means of transport' the first country that is an EU Member State must be the country of the 'CUSTOMS OFFICE OF FIRST ENTRY' or in case the COFE is "XI" then "GB" must be listed in the 'ACTIVE BORDER TRANSPORT MEANS/Countries of routing of means of transport' before any ICS2 country." Proposed wording: "The country of the COFE must be listed in the sequence of 'ACTIVE BORDER TRANSPORT MEANS/Countries of routing of means of transport'. In case the COFE begins with "XI" then "GB" must be listed in the 'ACTIVE BORDER TRANSPORT MEANS/Countries of routing of means of transport'." | Y |  | Y |  | 3 |  | 2.02 | N/A | In production |  | High | Medium
281 | 2023-09-27 | 5. ICS2-HTI-IE-(2022-05-04)-v2.02 | 2022-05-04 | 2.02 | IE3N08 Control notification | For the generation of the "Control notification" message on CR level for the different parties - Person notifying the arrival, Notify party, Declarant/Representative - each of these data elements have to be optional and filled in only when the message is destined to it. Hence, C3049 has to be removed from "Person notifying the arrival". | IE3N08 Control notification "Person notifying the arrival" to be modified from C to O and C3049 "If the Arrival notification is provided via a National Arrival System (not via the STI), then the ‘PERSON NOTIFYING THE ARRIVAL’ is O, else it is M." to be removed from the two messages. | Y | Y | Y |  | 3 |  | 2.03 | TBC | TBC | TBC | Medium | Low
283 | 2023-09-27 | 5. ICS2-HTI-IE-(2022-05-04)-v2.02 | 2022-05-04 | 2.02 | IExx10, IExx13, IExx17 | There is no "Transport document (House level)" class in the "Consignment (House level)". Even if there is no legal contract on a house level, the "Transport document (Master level)" has to be indicated there for consistency reasons by the EO (not by the CR). (IExx10, IExx13, IExx17 - ENS filing types) | IExx10, IExx13. IExx17 "Transport document (House level)" class to be added as M 1..1 in "Consignment (Master level)/Consignment (House level)". | Y |  | Y |  | 3 |  | 2.03 | In conformance | In production | 3.1.0.0 | High | Medium
298 | 2024-04-17 | 7. ICS2-HTI-CL-(2023-12-15)-v2.02 | 2023-12-15 | 2.02 | CL766 Risk assessment completeness status | The reference of CL766 "Risk assessment completeness status" has to be updated to CL768 "Risk assessment completeness status". | CL766 "Risk assessment completeness status" -> CL768 "Risk assessment completeness status" | Y |  | Y |  | 2 and 3 |  | 2.03 | In conformance | In production | 3.1.0.0 | Low | Low
299 | 2024-04-17 | 5. ICS2-HTI-IE-(2022-05-04)-v2.02 | 2022-05-04 | 2.02 | IE3N12/IE4N16 Pre-loading risk assessment status notification | The code list attached to the data element "Pre loading Risk Assessment Status/House consignment status information/House consignment status/Code" has to be changed from CL766 to CL768 (related to KEL entry 298). | IE3N12/IE4N16 Pre-loading risk assessment status notification "Pre loading Risk Assessment Status/House consignment status information/House consignment status/Code" CL766 -> CL768 | Y |  | Y |  | 2 and 3 |  | 2.04 | In conformance | In production | 3.1.0.0 | Low | Low
301 | 2024-04-24 | 6. ICS2-HTI-R&C-(2023-12-15)-v2.02 | 2023-12-15 | 2.02 | R3028 | R3028 content has to be aligned with the content of C3055 for the processing of receptacles when the request concerns the pre-loading risk assessment status of the related house consignments part of a receptacle. | R3028 "Either 'MRN' or 'TRANSPORT DOCUMENT' must be used." to be modified to "Either 'MRN', 'TRANSPORT DOCUMENT' or 'RECEPTACLE' must be used." | Y |  | Y |  | 2 and 3 |  | 2.03 | In conformance | In production | 3.1.0.0 | Low | Low
306 | 2024-06-04 | Business rules for validation on centrallized level | 2023-12-15 | 2.0.4 | Validation of the identification of consignor, consignee, buyer, seller | When an identification is provided for the following parties in the ENS filings - consignor, consignee, buyer, seller, then it has to be validated if it is an EORI or TIN against the relevant reference data. If not the ENS filing has to be rejected with the error 12 - Incorrect (code) value and pointer to the party data group. | Validation of the identification of consignor, consignee, buyer, seller Applicable to: All ENS filings and amendments Rule: When an identification is provided for the following parties in the ENS filings - consignor, consignee, buyer, seller, then it has to be validated if it is an EORI or TIN against the relevant reference data. If not the ENS filing has to be rejected via IE3N99 with the error "12" - "Incorrect (code) value" and pointer to the party data group. | Y |  | Y |  |  |  | 3.0.0 | In conformance | In production | 3.1.0.0 | High | Medium
311 | 2024-06-05 | 5. ICS2-HTI-IE-(2023-12-15)-v2.03 | 2023-12-15 | 2.03 | IExx52 | The "Total gross weight" and "Additional information" has to be added on a master consignment level and the "Weight" has to be added on a goods item level. | IExx52 "Total gross mass" Consignment (Master level)/Total gross mass as M 1..1 "Weight" Consignment (Master level)/Goods item/Weight as M 1..1 "Additional information" Consignment (Master level)/Additional information as O 0..99 | Y |  | Y |  |  |  | 2.04 | Q4/2026 | Q4/2026 | 3.3.0.0 | Medium | Medium
312 | 2024-06-04 | 5. ICS2-HTI-IE-(2023-12-15)-v2.03 | 2023-12-15 | 2.03 | IExx34 | The data class "Split consignment" to be removed. | IExx34 The data class "Split consignment" with data elements "Split consignment indicator" and "Previous MRN" to be removed from all IExx34 messages. This change to be implemented in the v4 of the IExx34 messages. | Y |  | Y |  |  |  | 2.04 (corrigendum) 3.00 (corrigendum) | Q4/2026 | Q4/2026 | 3.3.0.0 | Medium | Medium
321 | 2024-09-12 | ICS2-HTI-CL-(2023-12-15)-v2.02 | 2023-12-15 | 2.02 | CL723 Functional error code | A new error code to be added for the cases when there is an XSD error returned. | CL723 Functional error code 106 Syntax error | Y | Y | Y |  |  |  | 2.03 | Q3/2026 | Q3/2026 | 3.2.0.0 | Medium | Medium
323 | 2024-10-09 | 5. ICS2-HTI-IE-(2023-12-15)-v2.03 | 2023-12-15 | 2.03 | IE3Q05/IE4Q09 ENS Consultation | R3028 contains reference to the "Receptacle" data class but is not related to the data class in the message schema. | IE3Q05/IE4Q09 ENS Consultation "Receptacle" data class to be linked to R3028 | Y |  | Y |  |  |  | 2.1 | Q4/2026 | Q4/2026 | 3.3.0.0 | Low | Low
324 | 2024-10-25 | 5. ICS2-HTI-IE-(2023-12-15)-v2.03 | 2023-12-15 | 2.03 | IExx52, IExx53, IExx54, IExx55 | The "Identification number" for the Representative has to be an EORI as for the rest of the ENS filing types. | IExx52, IExx53, IExx54, IExx55 "Representative/Identification number" R3005 to be added. | Y | Y | Y |  |  |  | 3.00 | Q4/2026 | Q4/2026 | 3.3.0.0 | Medium | Medium
325 | 2024-10-25 | 5. ICS2-HTI-IE-(2023-12-15)-v2.03 | 2023-12-15 | 2.03 | IExx53, IExx54 | The mode of transport data element is missing for these two types of ENS filings and has to be introduced. | IExx53, IExx54 "Active border transport means / Mode of transport" n..1 M 1..1 CL018 IExA53, IExA54 "Active border transport means / Mode of transport" R3024 IExx54 "Supplementary declarant" modified from O to C with C3020. | Y | Y | Y |  |  |  | 3.00 | Q4/2026 | Q4/2026 | 3.3.0.0 | Medium | Medium
326 | 2024-11-28 | 5. ICS2-HTI-IE-(2024-11-15)-v3.00 | 2024-11-15 | 3.00 | IExx51 | There is no "Transport document (House level)" class in the "Consignment (House level)" for F51. Even if there is no legal contract on a house level, the "Transport document (Master level)" has to be indicated there for consistency reasons by the EO (not by the CR). | IExx51 "Transport document (House level)" class to be added as M 1..1 in "Consignment (Master level)/Consignment (House level)". IE3A51, IE4A51 "Consignment (Master level)/Consignment (House level)/Reference number" R3024 to be added. | Y |  | Y |  |  |  | 2.04 (corrigendum) 3.00 (corrigendum) | In conformance | In production | 3.1.0.0 | High | Medium
328 | 2024-11-28 | 5. ICS2-HTI-IE-(2024-11-15)-v3.00 | 2024-11-15 | 3.00 | IExx50 | The "Passive border transport means" on house consignment goods item level is not mandatory. | IExx50 "Consignment (Master level)/Consignment (House level)/Goods item/Passive border transport means" to be modified from M to O. Namespace version to be updated from v3 to v4. | Y |  | Y |  |  |  | 3.10 | Q4/2026 | Q4/2026 | 3.3.0.0 | Medium | Medium
331 | 2025-06-13 | Business rules for validation on centrallized level | 2024-11-15 | 3.1.0 | Validation for existence of previous ENS in case of re-entry/split | In case there is split consignment or re-entry simplification used, there is a validation performed that the previous ENS has to be found. In case no previous ENS is found, then the ENS filing is rejected. | In case any of the indicators - "Re-entry indicator" or "Split consignment indicator" - is set to "1", then then previous ENS is searched for by the ICS2 common repository. In case no previous ENS can be identified either based on the master transport document reference for the declarant or based on the "Previous MRN" included, an error will be returned via IE3N01 ENS Lifecycle validation with error code "105" No previous ENS found. | Y |  | Y |  |  |  | 3.2.0 | Q3/2026 | Q3/2026 | 3.2.0.0 | Medium | Medium
332 | 2025-09-23 | 5. ICS2-HTI-IE-(2025-04-03)-v3.00 | 2025-04-03 | 3.00 | IExx10, IExx13 | When the Consignee is not known in the bill of lading, the Notify party has to be indicated. Currently both the Consignee and the Notify party are optional and there is a risk that neither the Consignee nor the Notify party are provided. Therefore, the "Consignee" and "Notify party" in F10 and F13 have to be made conditional with C3022 and C3024 respectively. | IExx10, IExx13 "Consignment (Master level)/Consignment (House level)/Consignee" to be modified from O to C with C3022. "Consignment (Master level)/Consignment (House level)/Notify party" to be modified from O to C with C3024. The namespace to be modified from v3 to v4. | Y | Y | Y |  |  |  | 3.10 | Q4/2026 | Q4/2026 | 3.3.0.0 | Medium | Medium
333 | 2025-09-23 | 5. ICS2-HTI-IE-(2025-04-03)-v3.00 | 2025-04-03 | 3.00 | IExx11, IExx12 | The "Consignee" has to be mandatory at master level since F11 and F12 provide information for consolidated cargo and the Consignee is the freight forwarder. | IExx11, IExx12 "Consignment (Master level)/Consignee" to be modified from O 0..1 to M 1..1 The namespace to be modified from v2 to v3. | Y | Y | Y |  |  |  | 3.10 | Q4/2026 | Q4/2026 | 3.3.0.0 | Medium | Medium
334 | 2025-10-06 | 5. ICS2-HTI-IE-(2025-04-03)-v3.00 | 2025-04-03 | 3.00 | IExx57, IExx58 | There must be at least 2 countries of routing of the consignment. | IExx57, IExx58 The cardinality of "Consignment (Master level)/Consignment (House level)/Countries of routing of consignment" to be modified from 1..99 to 2..99. The namespace to be v4 (the messages will be implemented directly to v4). | Y |  | Y |  | 3.10 |  | 3.10 | Q4/2026 | Q4/2026 | 3.3.0.0 | Medium | Medium
335 | 2025-10-22 | 5. ICS2-HTI-IE-(2025-04-03)-v3.00 | 2025-04-03 | 3.00 | IExx56 | R3053 "The 'Estimated date and time of arrival' cannot be earlier than the 'Actual date and time of departure' or 'Estimated date and time of departure'." to be attached to the following data elements "Actual date and time of departure", "Estimated date and time of departure" and "Estimated date and time of arrival". | IExx56 Estimated date and time of arrival R3053 Estimated date and time of departure R3053 Actual date and time of departure R3053 The namespace to be v4 (the messages will be implemented directly to v4). | Y |  | Y |  |  |  | 3.10 | Q4/2026 | Q4/2026 | 3.3.0.0 | Medium | Medium
Note on L2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not relevant any more as there is only one version of the system in development, maintenance, operations. This column is kept for history.
Note on R2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The "Software release version" is included for the entries currently under implementation, not for all historical entries.

## Incidents PM KE
# | PM/KE | Description | Requester MS/EO | PROD/CONF | Incident | Incident registration date | When to be fixed in conformance (the indicated timing can vary and will be updated in case of a change) | When to be fixed in production (the indicated timing can vary and will be updated in case of a change) | Software Release Version | JIRA | To be communicated to trade | Priority | Impact
2 | KE23620 | ICS2-R2-E2E-NA.DE: XXX: Missing IE3N08 IE3N08 not generated to the EO. Reason - due to not available master transport document in the ENS filing structure. | EO | PROD and CONF | IM607090 | 28/06/2023 | N/A | In production |  | ICS2-7925 | Yes | Low | Low
4 | KE23657 | ICS2-R2-PROD: message type IE4A26 in erorr on OAQ RA_PREPARATION_TABLE ICS2-R2-PROD-EO: LifeCycle Error - Original Filing Not Found The CR application needs to be updated to handle these cases that might lead to an exception from Oracle "ORA-01795: maximum number of expressions in a list is 1000". In principle, all queries with IN clause will be updated, and in case more than 1000 elements need to be queried, the list will be split per 1000 elements and the respective query will run in batches of 1000 elements. | EO | PROD and CONF | IM608903 IM613727 | 04/07/2023 24/07/2023 | N/A | In production |  | ICS2-7960 | Yes | High | High
6 | KE23661 | ICS2-R2-PROD-NA.DE: Pre-Arrival Analysis completed while Pre-Loading Analysis is ongoing When a Master filing is amended, for which PLACI Air Pre-loading RAs are ongoing, these PLACI Air Pre-loading RAs are updated with the new FULL_RA_REFERENCE generated by the amendment. However, the previous pre-Arrival RA reference, which is no longer "linked" to the ongoing PLACI Air Pre-loading RA, is identified by the scheduled job as "Ready for dispatch" as it cannot locate any associated PLACI Air Pre-Loading RA with pending results. | DE | PROD | IM610360 | 10/07/2023 | N/A | In production |  | ICS2-7112 | Yes | High | High
10 | KE23699 | ICS2-R2-EO: Again an N99 with MRN MRN is used as functional reference in IE4N99 and subsequently in IE3N99 instead of LRN when the filing is rejected due to data cleansing violation | EO | PROD | IM635288 | 16/10/2023 | N/A | In production |  | ICS2-7517 | Yes | High | High
12 | KE23701 | ICS2-R2-PROD-EO: ENS lifecycle validation error received after amendment The IE4Q02 generation fails if RiskAnalysisResultCode of the previous RAs is NULL, the case stated above results that the message is present in RA_PREPARATION error queue and the ENS filing is not stored. | EO | PROD | IM610932 | 12/07/2023 | N/A | In production |  | ICS2-8087 | Yes | High | High
13 | KE23718 | ICS2-R2-CT: ICS2 CONF - F42 accepted with the same MAWB number EO reported that it was able to lodge two F42 ENS filings (with MRN: 23NL0400003YPFSAT8 and 23NL0400003YX3FAT2) containing identical information. This is due internal processing. DB DML statement will be provided to cleanup/remove records of UDC04-F42 on a daily basis. | EO | PROD | IM613123 | 20/07/2023 | N/A | In production |  | ICS2-8135 | Yes | High | High
15 | KE23750 | ICS2-R2-PROD-STP: Default Communication Path can't be deleted A list of configurable elements per EO are only visualized with no option to be edited - they need to be made editable in order to be possible to be modified. | DE | PROD | IM613983 | 25/07/2023 | N/A | In production |  | ICS2-8197 | Yes | Medium | Low
18 | KE23815 | ICS2-R2-PROD-STP: supplementary declarant The optionality is not correct for the ENS Filings IEX15, IEX22, IEX26, IEX33. | EE | PROD | IM624064 | 05/09/2023 | N/A | In production |  | ICS2-8362 | Yes | Low | Low
20 | KE23817 | ICS2-R2-STP: Follow up to IM623719 STI STP UI does not support hyphen in Transport Document Number. Currently the use of hyphen for this field is supported only in S2S communication. STI STP UI should be aligned according to the CFSS requirements which indicate that Transport Document Number is an alphanumeric field without any other restrictions. | Internal | PROD | IM625516 IM623719 | 11/09/2023 04/09/2023 | N/A | In production |  | ICS2-8467 | Yes | High | High
22 | KE23819 KE23926 | ICS2-R2-PROD-STP-NA.SK: No error message IE3N99 delivered nor displayed in STI-STP user interface According to CFSS notifications could be sent to different actors depending on the business scenario. At the case where the ENS filing was lodged by representative, the IE3N99 was supposed to be delivered to person filing which in this particular case was representative (and not a declarant). ICS2-R2-PROD-NA.EE: Referrals to representative According to definitions "Person filing means any person that submits to the customs authority ENS filing ..." and it can be declarant or representative. | SK EE | PROD | IM615347 | 31/07/2023 | N/A | In production |  | ICS2-8429 | Yes | High | High
23 | KE23874 | ICS2-R2-NA.DE: Error received trying to send F20 in STI-STP There is a malfunction in processing the field Gross Mass in Goods Items. More specifically when it is the last field that gets changed from the user, its value becomes of type string. Since the value of the field must be of type number, this results to an unsuccessful submission. | DE | PROD | IM626545 | 13/09/2023 | N/A | In production |  | ICS2-8626 | Yes | Medium | Medium
25 | KE23935 | ICS2-R2-EO: Cannot delete Access Point in STI-STP Conf During the update of access point configuration of manage preferences, if the user changes only the Certificate Authority, the update completes successfully but the new data is not persisted. | DK | PROD | IM633913 IM633604 | 10/10/2023 09/10/2023 | N/A | In production |  | ICS2-8745 | Yes | Medium | Medium
26 | KE23941 | F26 linking query under certain business scenarios returns huge result set. The filtering which is applied to the result set results to high cpu consuption when multiple F26 are processed in parallel | Internal | PROD | IM637396 | 23/10/2023 | N/A | In production |  | ICS2-8845 | Yes | High | High
27 | KE23946 | The following issue has been identified in the context of IM630538. CR sends two IE4N11 messages to the same party when Carrier and Person filing (Declarant) are the same. As per BPML4 Process description for "G-06-01-03 – Control notification to be sent to Carrier? The Carrier is to be notified when • Carrier holds the AEOS authorisation; • Carrier is different from the Person filing; CR will be enhanced in order upon the acceptance of IE4N11 from NES, to check if the contained Person filing is the same person as the contained Carrier and in this case to send only one message IE4N11 to STI. This is not a blocking issue for the operations. | GR | PROD | IM630538 | 28/09/2023 | N/A | In production |  | ICS2-8810 | Yes | Medium | Low
29 | KE23979 | EO reported that they are not receiving replies (No N99, No R01, N03) to the submitted F24 or A24 messages. The identified issue is applicable for CONF due to dummy data. | EO | CONF | IM599073 | 26/05/2023 | N/A | In production |  | ICS2-7252 | Yes | Low | Low
32 | KE23986 KE24021 | ICS2-R2-PROD-NA.DE: Unknown MRN - Original Filing not found The F21 linking fails due to transaction timeout, the issue have been identified in cases when more than 100+ F26 and 15K HC in total are referenced by the F21. | DE BG | PROD | IM641248 | 07/11/2023 | N/A | In production |  | ICS2-8980 | Yes | High | High
35 | KE24020 | ICS2-R2-PROD-NA.GR: IE4Q02-23GR02000BENRPZAT2 FullRaDetectionScheduledTask fails to complete due to transaction timeout when the application (FullRaTriggerJmsClient) sends the maximum amount of 4Q02 messages (500) and the messages are big. | GR | PROD | IM639794 | 01/11/2023 | N/A | In production |  | ICS2-9008 | Yes | High | High
37 | KE24046 | ICS2-R2-PROD-EO: no reply The firm XXX has sent a F43, but there is no reply : and when isearch into the BS MON or message store I found only a a message from Trader to STI but without any reply. # The first IE3F43 was rejected from CR due to data cleansing and due to the known error STI used MRN value instead of LRN. # The IE3Q05 correctly rejected as the MRN was not valid. # The IE3F43 rejected from CR because TDN is already submitted. Although the filling in step 1 was rejected, thus they believe that the transport document should not be registered from step 1 but from another third filling. As per SOFTDEV CR analysis, the problem you are facing is caused due to Known Issue corrective Jira ICS2-8351, where the ENS Lifecycle Validation (T-02-03) was performed before the Data Cleansing process (T-02-24, T-02-25, T-02-26). | EO | PROD | IM648950 | 30/11/2023 | N/A | In production |  | ICS2-8351 | Yes | Medium | Medium
41 | KE24154 | ICS2-R2-PROD-EO: IE3N99 cannot be related EO informed that they received the attached IE3N99 in PROD environment, which does not contain a functional reference or MRN. Thus they were not able to relate the error message. When a IE3Q05 be submitted to STI and the respective IE4Q09 rejected by CR with unknown MRN/Transport Document the value of the functional reference is missing from the IE3N99 message. More specifically, IE3N99 messages needs to include the value of functional reference, hence the EO can correlate this message with the respective IE3Q05. | EO | PROD | IM659973 | 09/01/2024 | N/A | In production |  | ICS2-9340 | Yes | Low | Low
42 | KE24167 | ICS2-R3-CT-EO: CONF for XXX (House Filer F14 Most Common) When a mock message is created from EO self Mock the necessary data from the submitted message, is used to fill the created message. In case the UNLOCODE is used inside the submitted message instead of the address/country the message cannot be created. EO self Mock need to be enhanced to accept the UNLOCODE in mock messages creation. Use address/country instead of UNLOCODE in all "places" inside the IE3F14 (placeOfAcceptance, placeOfDelivery) and re-execute the flow. | EO | CONF | IM661211 | 12/01/2024 | N/A | In production |  | ICS2-9391 | Yes | Low | Low
47 | KE24228 | ICS2-R2-CT-EO: Issue in the execution of the F21 Most Common (Mandatory basis) scenario (Follow up of IM658751) When a mock message be created from EO self Mock the necessary data from the submitted message, used to fill the created message. In Carrier F21 Referrals/Mandatory basis/Controls and Arrival notification flow, if the IE3F21 message contains the element transportEquipment in Master Consigment/House Consignment/ Goods items level the EO self Mock does not populate this value in the mocked IE3F26. EO-self-conformance-mock needs to be updated to check if the transportEquipment in Master Consigment/House Consignment/ Goods items level is populated in IE3F21 and to populate it in IE3F26 message if this is necessary. The EO should reset the flow and re-execute it, using transport Equipment in Master Consignment level in the constructed IE3F21 that they submit. EO-self-conformance-mock needs to be updated to check if the transportEquipment in Master Consigment/House Consignment/ Goods items level is populated in IE3F21 and to populate it in IE3F26 message if this is necessary. | EO | CONF | IM666928 | 29/01/2024 | N/A | In production |  | ICS2-9452 | Yes | Medium | Medium
49 | KE24255 | ICS2-R3-CT-NA.DK: Issue in the execution of Notify Party (Sea edition) Business scenario (follow up of IM669447) EO-self-conformance-mock needs to be updated to send all IE3N06 in Business Scenario F10 for Notify Parties. In current implementation the second IE3N06 is missing from the mocked messages. EO-self-conformance-mock will be updated to include the missing message. | DK | CONF | IM671031 | 09/02/2024 | N/A | In production |  | ICS2-9564 | Yes | Low | Low
50 | KE24256 | ICS2-R2-PROD-NA.DE: IE3N01 does not comply to message specifications ICS2-CR produces syntactically invalid IE4N01 as the messageElementPath exceeds the length of 512 characters as it is defined in the MessageElementPathContentType when multiple message elements path are concatenated. | DE | PROD | IM667370 | 30/01/2024 | N/A | In production | 3.0.1.0 | ICS2-9589 | Yes | Low | Low
53 | KE24278 | A bug was discovered that could cause the application to hang when an EO tries to access the Self-Conformance Test Campaign page. The bug occurs when some network calls get a delayed response causing the application to enter an undefined state and become unresponsive. | EO | CONF | IM663007 | 18/01/2024 | N/A | In production |  | ICS2-9530 | Yes | High | Medium
54 | KE24282 | The generated error notification (IE3N99) has to contain message element path pointing to existing data elements in the corresponding arrival notification (IE3N06). | EO | PROD | IM651993 | 08/12/2023 | N/A | In production | 3.0.1.0 | ICS2-9537 | Yes | Low | Low
55 | KE24292 | Following investigation for incident ICS2-9608 we can confirm that the issue is a bug of the STI-STP application. Specifically the issue stems from a miss-mapping in the DTO mapper. We map on both Transport document (Master level) number and Transport document (House level) number the same value from the DTO we receive: The scope of this RfC is fixing the described behavior and investigating if the same issue appears in other Filings | EE | PROD | IM673163 | 14/02/2024 | N/A | In production |  | ICS2-9610 | Yes | Medium | Medium
57 | KE24303 | IE3R02 when submitted S2S cannot be retrieved via the STI STP. | DK | PROD/CONF | IM676209 | 23/02/2024 | N/A | In production | 3.0.0.0 | ICS2-9676 | Yes | Medium | Low
58 | KE24306 | EO-self-conformance-mock trying to create the mocked message IE3F12 but failed if the notify party is empty in the submitted IE3F14/F15. The script will be adapted not to check for a "Notify party" in the submitted by the EO ENS filings during the execution of the test scenarios. Until the fix of this issue the EO has to fill in the "Notify party" in the lodged F14/F15 as part of the EO Self-conformance campaigns. | EO | CONF | IM677888 | 28/02/2024 | N/A | In production |  | ICS2-9416 | Yes | Medium | Low
61 | KE24319 | Following investigation of incident IM679742/ICS2-9749 an issue was discovered in the Create ENS Filing module when filling a Filing in which rule R3011 is applied. The rule states that when the Mode of Transport field has the value "1 - Sea transport", the Type of Identification is forced to have the value "10 - IMO Ship identification Number". We implement this on the UI part of the application by pre-filling and disabling the Type of Identification field when the EO selects "1 - Sea transport" as a Mode of Transport to block him from making further changes. The issue is that when submitting the Filing the value of Type of Identification field is send as null, hence it cannot be mapped and get rejected by the REST layer. | DK | PROD | IM679742 | 04/03/2024 | N/A | In production | 3.0.0.0 | ICS2-9751 | Yes | High | Medium
63 | KE23136 | During EO's conformance testing, a successfully sent IE3Q05 and IE3R08 successfully recevied was not marked as part of the conformance campaign. As per SOFTDEV analysis, there is an issue in the STI Submission handler. | EO | CONF | IM571977 | 09/02/2023 | N/A | In production | 3.0.0.0 | ICS2-6893 | Yes | Low | Low
65 | KE24419 KE24420 | EO Self-conformance scenarios related to the testing of F12 - no transport equipment, location/UNLOCODE (expected from the content of the F12) to be used in the mocked messages. Some hardcoded values to be used in the mocked messages. | EO | CONF | IM661211 IM685596 IM686812 IM687161 IM687165 | 12/01/2024 21/03/2024 26/03/2024 27/03/2024 27/03/2024 | N/A | In production |  | ICS2-9865 ICS2-9391 | Yes | Low | Low
66 | PM26768 | No "Notify party" expected in the submitted F14/F15 ENS filings during the execution of the EO Self-conformance test scenarios. There was an issue identified requiring the "Place of delivery" and the "Countries of routing of consignment" in the submitted F14/F15 to have a particular country. This dependency/limitation will be removed. | EO | CONF | IM662300 IM669792 IM677888 IM685596 IM686812 IM687161 IM687165 | 16/01/2024 06/02/2024 28/02/2024 21/03/2024 26/03/2024 27/03/2024 27/03/2024 | N/A | In production |  | ICS2-9416 | Yes | Medium | Low
67 | KE24455 | No proper mock-up of the house transport document in the simulated IE3R02 for the F12 and F21 referrals. | SE EO | CONF | IM677863 IM694785 | 28/02/2024 16/04/2024 | N/A | In production |  | ICS2-9692 | Yes | Medium | Low
68 | KE24443 | When trying to perform Self-Conformance Test test scenarios keep getting stuck in status "Execution pending", when the system should be sending various kinds of notifications. EO-self-conformance-mock submit the mocked message IE3F12 but rejected from validation bas if the placeOfUnloading is not DE, in the submitted IE3F14/F15. EO-self-conformance-mock needs to be updated to use the placeOfAcceptance / placeOfDelivery from the submitted IE3F14/F15 to construct the CountriesOfRoutingOfMeansOfTransport in the ActiveBorderTransportMeans of the IE3F12. | DK EO | CONF | IM694784 | 16/04/2024 | N/A | In production |  | ICS2-9588 | Yes | Medium | Low
70 | KE24454 | In STI-STP conformance environment when filling in F10 or F11 ENS the identification/EORI-number for seller and buyer is mandatory. It was discovered that "Identification Number" field for both Buyer and Seller on the Goods Shipment tab of House Consignments is marked as mandatory for all the relevant Filings on the STI-STP application. According to the CFSS those fields should be optional. | EO FI | STI-STP | IM695879 | 19/04/2024 | N/A | In production |  | ICS2-10071 | Yes | Low | Low
71 | KE24460 | EO-self-conformance-mock trying to create the mocked message IE3F21 but failed if the countriesOfRoutingOfConsignment has not countries with sequence started with number 1 and ended with the size of the list. EO-self-conformance-mock needs to be updated to retrieve the first and the last country from countriesOfRoutingOfConsignment independently from the sequence number (E.G seq started with 0 or 500) Impacted flows: F26 Mandatory basis, F26 Referrals, F26 AEO Control notification, F26 ENS Pending notification, F22 Mandatory basis, F22 Referrals, F22 AEO Notification, F22 AEO Notification, F22 AEO Notification, Express (F21 + F32 + F33). | EO | CONF | IM695467 | 18/04/2024 | N/A | In production |  | ICS2-9553 | Yes | Low | Low
75 |  | It was identified that after the initial lodgement of ENS's based on F42, its invalidation and the lodgement of new F42 the related house consignments from the corresponding F43/F44 are not linked to the newly lodged F42. This is due to the fact that for the linking of house consignments to ENS a pre-condition is their "pending linking" state. However, in this case they appear as "Linked" so they are not identified by the system for linking to the newly lodged F42. To remove this pre-condition KEL entry 302 has been registered for the postal house consignments. For the rest of the ENS filing types the following KEL entries have been registered - 303, 304, 305, 308, 309, 310. | HR | PROD | IM703969 | 15/05/2024 | N/A | In production | 3.0.2.0 | ICS2-10276 | Yes | High | High
77 | KE24569 | An economic operator submitted 40 F26 filings. They were supposed to link with F21 filing of another economic operator, but the linking according to Finnish customs did not take place. Attached is a list of F26 filings with all of the MRNs. During the investigation of transaction timeouts thrown in PROD during the Q02 generation process, we've identified cases for which the retrieval of ENS_ENTITY_STATE _TRANSITION entities are not batch BATCH loaded, resulting to a query invocation per ENS_ENTITY. The issue we've detected and we'll resolve under the specific RfC is the retrieval of ENS_ENTITY_STATE_TRANSITION sub-entities. The issue was that for each ENS_ENTITY ICS2 CR issued a single query to retrieve ENS_ENTITY_STATE_TRANSITION while the new approach is to retrieve them in batches of 1000 ens entities, the change will reduce the execution time of the ra preparation time. | EE | PROD | IM705871 | 21/05/2024 | N/A | In production |  | ICS2-10301 | Yes | High | High
78 | KE24570 | In MON&BS CONF I found that tooltip for pen/pencil icon is Load, but I believe this is error as for load in MON&BS we have another icon. I assume the problem persist also in PROD environment but I can not check it. In MON&BS Trader Preferences -> Edit Trader Access Point Configuration the tooltip for pen/pencil icon is Load, but It should be Edit. A wrong translation key was used | MS | CONF MON | IM709177 | 30/05/2024 | N/A | In production | 3.0.1.0 | ICS2-10327 | Yes | Low | Low
80 | KE24590 | We noticed in STI-STP production that there is only EU countries in the Nationality menu. All nationalities should be on the menu. Now this is a major issue that should be fixed as soon as possible. Upon investigation of ticket ICS2-10390 the field of nationality in ens filing information section uses a codelist CL717 including only the EU countries whereas it is required to use the codelist CL718 including all the available countries. The scope of this ticket is to implement the above change. | FI | STI-STP | IM712886 | 10/06/2024 | N/A | In production |  | ICS2-10398 | Yes | High | Low
83 |  | Due to the size of CL244/CL144 its values cannot be retrieved synchronously so another approach has to be taken for the STI-STP. (currently under assessment) As a workaround at the moment it is adviced that the alternative of the UNLOCODE is used - the combination of country and location in the STI-STP. | NL | STI-STP | IM698032 | 25/04/2024 | Q3/2026 | Q3/2026 | 3.2.0.0 | ICS2-10262 | Yes | Medium | Low
85 |  | It will be ensured that first the ENS Registration response (IE3R01) is communicated to the EO's before the Assessment complete notification (IE3N03). | EO | STI-STP | IM660168 | 10/01/2024 | N/A | In production | 3.0.1.0 | ICS2-9199 | Yes | High | High
87 | KE24716 | ICS2-R3-PROD-EO: Missing response for IE3N06 EO reported that they are missing a response for the arrival notification with a particular LRN. During investigation of ICS2-10623, ICS2-10628 and ICS2-10631 we found that in case the submitted IE3N06 contains at least 1 notify party with valid preferences (registered from STP) and at least 1 notify party with invalid preferences (not registered in STP), STI cannot dispatch any IE3R04 to the respective EOs. STI needs to be updated to send all IE3R04 notification messages to the EOs who has valid trader preferences(registered from STP). | EO | PROD STP | IM725653 | 18/07/2024 | N/A | In production | 3.0.0.2 Hotfix | ICS2-10640 | Yes | Medium | Low
88 | KE24717 | ICS2-R3-PROD-EO: Invalid IE3N99 received - messageElementPath exceeds 512 characters EO informed that they received an invalid IE3N99 message (messageID: 53027b916c6a-4add-a4de-77eea0051224). The messageElementPath contains more than 512 characters, which is not correct according to the XSD-specifications. Due to the erroneous assignment of the same Transport Document Number to each house consignment in an ENS filing, the application generates an invalid IE4N99 message. The IE4N99 produced by the ICS2-CR is syntactically invalid as the messageElementPath exceeds the length of 512 characters as it is defined in the MessageElementPathContentType. | EO | PROD | IM726045 | 19/07/2024 | In conformance | In production | 3.1.0.0 | ICS2-10643 | Yes | Medium | Low
90 | KE24752 | ICS2: IE3Q04 did not receive a response EO reported that they sent an IE3Q04 for MRN: 24DE02000GBKFE5AT4 but did not receive a response (IE3R07). According to ICS2 MON, two IE3Q04 were received from STI and in both cases IE4Q06 was sent to the CR, but no response was sent to the Trader. The IE3Q04 was not processed by the system due to a known issue with the processing of amendments for master ENS filings. | EO | PROD | IM727604 | 25/07/2024 | In conformance | In production | 3.0.2.0 | ICS2-10720 | Yes | Medium | High
91 | KE24754 | ICS2-R3-PROD-EO: EO is missing Assessment Complete for 10 MRN This corrective RfC has to be registered for the fixing the linking expiration timer that does not expire after the amendment. It was confirmed that it is started but from the sequence of events we do not see anything happening upon its expiration. | EO | PROD | IM724915 | 16/07/2024 | N/A | In production | 3.0.1.0 Service patch | ICS2-10053 | Yes | High | High
93 | KE24818 | In case the "Goods shipment" are optional in an ENS filing due to C3020 (IE3A10, IE3A11, IE3A15, IE3A16, IE3A16, IE3A50, IE3A51) and the ENS filing is attempted to be amended then the amendment is not processed, does not re-trigger the risk analysis or any error. The amendment is neither accepted, nor rejected. This is due to an issue in the processing of the goods shipment information. | ES | PROD | IM742286 | 09/09/2024 | In conformance | In production | 3.0.2.0 | ICS2-10919 | Yes | Medium | Low
96 | KE24851 | An EO has requested support for the reasons behind not receiving a successful validation of the Notify party scenario during the EO self-conformance. Due to other ongoing ICS2 testing activities, a configuration was enabled that introduces a two-minute delay in the dispatch of risk analysis requests. As a result, steps 5-8 (assessment complete) were not executed in time before the reception of the arrival notification in step 9 (IE3N06). Additionally, we observed that the two arrival notifications were sent within 3 seconds of each other. To ensure a smooth execution, we recommend waiting for the IE3N08, which marks the completion of step 16, before sending the second arrival notification. The EO-mock to be updated to send the second IE3N06 upon the receipt of IE3N08 in Notify Party F10. | EO | STI CONF EO Self-conformance | IM737739 | 27/08/2024 | N/A | In production | STI 3.0.1.1 Hotfix | ICS2-11065 | Yes | High | Low
101 | KE24954 | An ITSP cannot configure a default communication path for a client. The PartyIds that can be added to the Default Communication Path of an EO are currently limited to values pre-set in the Access Point Configuration for that EO. This rule was added for Declarants who are also acting as Senders, but it should not be applicable for those Declarants who are not Senders (use an IT provider as their Sender). This behaviour is correct in STI-STP Trader Preferences but not in ICS2-MON. Workaround: The trader preferences to be created from the STP UI. | NL | ICS2 MON | IM766512 | 05/11/2024 | In conformance | In production | 3.1.0.0 | ICS2-11269 | Yes | Medium | Low
105 | KE25086 | During an EO self-conformance campaign an ENS filing is sent and, consequently, both registered (MRN generated) and rejected (IE3N99 generated). The contained error is 100 "Not Satisfactory Data Quality" pointing to an a party name. There is a bug identified in ICS2 leading to both accepting and rejecting the same ENS filing. After fixing the bug, the ENS filing will be only rejected, no MRN will be generated. The workaround in this case is to make the party name with less characters or excluding the special character. | EO | CONF/PROD | IM774864 | 28/11/2024 | In conformance | In production | 3.0.2.1 | ICS2-11356 | Yes | High | Medium
107 | KE25115 | When an unscheduled unavailability is recorded in the ICS2 MON&BS tool, the BCP is automatically activated 30 minutes after the unavailability was recorded. If after 30 minutes this unavailability is updated to set the end date and time in the past, the active BCPs are deactivated with current end date and time. In this case a mail needs to be sent to notify the mailing list subscribers about the BCP-deactivation. There is a bug in the code preventing this mail to be sent (the data in the database is saved properly). | DG TAXUD ITSM OPS | PROD MON BS | IM778098 | 05/12/2024 | In conformance | In production | 3.1.0.0 | ICS2-11473 | Yes | High | Low
110 | KE25185 | We have identified a missing IE4Q02 messages for ENS with MRN 25BG01000JLIPITAT4 in our NES.BG, it is visible in ICS2 Business Statistics & Monitoring but was not sent to BG NES. Please resend the missing IE4Q02 messages for 25BG01000JLIPITAT4. After conducting our investigation for incident ICS2-11687, we concluded that the the IE4F10 that was lodged did not have location at 'CONSIGNMENT (MASTER LEVEL)/PLACE OF LOADING' path. According to IE4F10 XSD this value is conditional and as described in C3007: "IF 'CONSIGNMENT (MASTER LEVEL)/PLACE OF LOADING/UNLOCODE' is not provided, THEN this attribute/class is M, ELSE it is not used.". During the identifications of the business case (CBR14 - Sea cases), CR does not properly handle the above conditional value resulting in null pointer exception and no IE4Q02 was generated. The issue will be fixed in order to properly implement C3007 for the identified business case which has to be deep-sea non-containerised. | BG | PROD | IM783106 | 16/12/2024 | In conformance | In production | 3.0.3.0 | ICS2-11760 | Yes | High | Medium
111 | KE25206 | EO is reporting missing responses to sent messages in conformance since last Friday. The last message sent was a F14 with LRN X. They are reporting receiving only the IE3R01 for the F14, they have not received the IE3N03. During the investigation an error was found on EO-mock when the LRN valuecontains "_". The application tries to retrieve the business case status SID number from the "new" correlation ID format (the one contains the business scenario version.) As a workaround no "_" has to be used in the the LRN. | EO | CONF | IM803027 | 28/01/2025 | In conformance | In production | 3.1.0.0 | ICS2-11283 | Yes | High | Low
112 | KE25213 | When creating an IE3F15 in ICS2 STI-STP CONF environment ‘Goods Shipment’ data element should only be mandatory when ‘Place of delivery’ is within the EU. In the attached example (STI-STP-F15-Example.png) the ‘Place of delivery’ is USA and the ‘Goods Shipment’ data element should therefore not be mandatory, and you should be able to Submit the ENS without filling in the ‘Goods Shipment’ details, but you cannot. C3020: If 'CONSIGNMENT (HOUSE LEVEL)/PLACE OF DELIVERY/UNLOCODE' 2 first characters or 'CONSIGNMENT (HOUSE LEVEL)/PLACE OF DELIVERY/ADDRESS/Country' refers to EU MS, THEN this class is M, ELSE it is O. It was discovered that for ENS Filing IE3F15, the fieldgroup 'Goods shipment' which includes the 'Buyer' and 'Seller' actors is always set as mandatory. | DK | CONF STI-STP | IM803430 | 29/01/2025 | In conformance | In production | 3.1.0.0 | ICS2-11828 | Yes | High | Low
114 | KE25256 | The attachments from messages from the economic operators which were submitted via AS4 cannot be accessed via the STP. After this is fixed, all attachments from messages (before and after the implementation of the change) from the economic operators submitted via AS4 (S2S) will be available for access via the STP. | EO | STI-STP | IM812239 | 18/02/2025 | In conformance | In production | 3.1.0.0 | ICS2-11595 | Yes | Medium | Low
116 | KE25270 | For the EO self-conformance scenarios which include IE3N09/IE4N11 the submitted master ENS filing should not contain "Transport equipment" at master consignment/goods item level. If there is "Transport equipment" included, then IE3N09/IE4N11 cannot be generated, hence, the scenario cannot be successfully executed. Workaround: No "Transport equipment" to be included on master consignment/goods item level in the submitted master level ENS filings for the scenarios including IE3N09. | EO | CONF | IM805978 | 04/02/2025 | In conformance since 08/12/2025 | N/A | 3.1.1.1.0 HF | ICS2-12110 | Yes | Medium | Low
118 |  | Correction for the number of the goods item in the error pointer in IE3N99/IE4N99 - in case the error pointer contains a reference to the goods item from an ENS filing, then the error pointer has to contain not only the identifier of the house consignment but also the goods item number from the goods item entity, not an automaticall generated one. Workaround: Currently, the counting of the goods item in a house consignment starts from 0 and does not consider the goods item number from the goods item. In case a goods item number is indicated in the error pointer, then the economic operator has to consider that the goods item pointed is the included number +1. | DG TAXUD | PROD/CONF | IM827204 | 19/03/2025 | Q3/2026 | Q3/2026 | 3.2.0.0 | ICS2-12369 | Yes | High | Low
119 |  | It is possible in the STP for a sender to lodge an Arrival notification for a Person notifying the arrival irrespective of the existing delegations between the users. This will be kept. What will be adapted in the STP is that the sender of the Arrival notification will have access to the related to the Arrival notifications notifications - IE3N06, Arrival notification itself, IE3R04 Arrival registration response, IE3N07 House consignment in incorrect state notification, IE3N08 Control notification, IE3N99 Error notification. Currently those notifications are accessible only to the parties indicated in the Arrival notification - Person notifying the arrival and the Notify party. Workaround: In case the sender needs access to the related notifications to the Arrival notification, they have to be listed as a Notify party. | HR | PROD/CONF | IM805812 | 04/02/2025 | Q3/2026 | Q3/2026 | 3.2.0.0 | ICS2-12243 ICS2-12406 | Yes | Medium | Low
121 | KE25311 | There is a problem identified for the uploading of a IE3Q04 message as XML file in the STP. Workaround: As a workaround the EO can invalidate the ENS Filing when viewing the IE3F10 Filing. They should navigate to the 'Search for Submission' page, locate the relevant IE3F10 ENS Filing and select it to view and from the 'Actions' menu on the top right select the 'Submit Invalidation' action. | ES | STP | IM824177 | 12/03/2025 | In conformance | In production | 3.1.0.0 | ICS2-12181 | Yes | Medium | Low
122 | KE25317 | In the scenarios which are related to the request for additional information referral, the type is AMD even if the RfI response is expected. Workaround: Even if the IE3Q02 Additional information request contains request type "AMD", the person filing can still send the related IE3R02 Additional information response, allowing the test to be completed. | EO | EO Self-conformance | IM819668 | 05/03/2025 | Q3/2026 | Q3/2026 | 3.2.0.0 | ICS2-12189 | Yes | Low | Low
124 | KE25363 | Not all mails related to a BCP activation were sent to the economic operators due to a high number of configured mails. An EO has configured more than 200 mail recipients. From a technical point (hidden for the economic operators) in case there are more mails configured than this limit, then the recipients have to be split in separate batches. Workaround: For an economic operator to be sure that all mails related to BCP unavailability communication are sent out, until this is fixed the number of mails configured should not exceed 200. | DE | PROD | IM801721 | 27/01/2025 | In conformance | In production | MON 3.1.0.0 | ICS2-12310 | Yes | High | Medium
127 | KE25377 | In STP, if the declarant includes a new line character in the field "Description of Goods", the ENS filing submission fails. Workaround: No new line character to be included in the elements of the ENS filing. | EO | STP | IM832684 | 02/04/2025 | In conformance | In production | STP 3.1.0.0 | ICS2-10772 | Yes | High | High
128 | KE25402 | In ICS2-STP for "Create ENS filing" for the fields 'ACTIVE BORDER TRANSPORT MEANS/Countries of routing of means of transport' and 'HOUSE CONSIGNMENTS/Countries of routing of consignment', no duplicate entries are allowed. This behavior is problematic since there are cases that require duplicate entries. One such case is when an EO wants to file from United Kingdom to North Ireland. According to R3018 "The country of the COFE must be listed in the sequence of 'ACTIVE BORDER TRANSPORT MEANS / Countries of routing of means of transport'. In case the COFE begins with 'XI', then 'GB' must be listed in the 'ACTIVE BORDER TRANSPORT MEANS / Countries of routing of means of transport'." In that case the EO would have to use the values GB and GB in the 'Countries of routing of means of transport' field but the system wouldn't allow him. The issue does not exist when the ENS filing is submitted S2S. Workaround: The ‘Upload Several ENS Filing’ page of the application can be used for the submission of ENS Filing in .xml format when duplicate countries have to be entered in the countries of routing. | EO | STP | IM832905 | 02/04/2025 | In conformance | In production | STP 3.1.1.0 | ICS2-12463 | Yes | High | Low
129 | KE25383 | In ICS2-STP for "Create ENS filing" the data class "Additional fiscal references" (applicable for F32 and F43) is optional. In the UI the data class "Additional fiscal references" appears as optional but upon the validation of the submission, the contained two data classes - "VAT Identification number" and "Role" - are incorrectly expected to be present for successful submission. Workaround: The ‘Upload Several ENS Filing’ page of the application can be used for the submission of ENS Filing in .xml format without the class "Additional fiscal references". | DE | STP | IM833390 | 04/04/2025 | In conformance | In production | STP 3.1.0.0 | ICS2-12372 | Yes | High | Low
130 | KE25384 | In ICS2-STP for ENS filing IE3F11 the field 'Active border transport means/Identification number' is marked as optional in the UI while according to the CFSS that field should be mandatory. Upon the submission of the ENS filing it is validated and respectively the data element value is expected. If not available, then the ENS filing is rejected. Workaround: 'Active border transport means/Identification number' is provided by the economic operator when filling in F11. | LV | STP | IM834942 | 09/04/2025 | In conformance | In production | STP 3.1.0.0 | ICS2-12425 | Yes | High | Low
131 | KE25422 | The following discrepancy between the conformance and production ICS2 STP where the Actors' data segment is not available in the production environment. The rootcause is a technical issue to be fixed (fixed in production via workaround CM99688). | MT | STP | IM830895 | 28/03/2025 | In conformance | In production | STP 3.1.0.0 | ICS2-12319 | Yes | High | Low
132 | KE25449 | In case when explanation is not filled in by the NSD or CSD when creating/updating unavailability report in the corresponding e-mails it is written "Explanations: No explanation provided by the reporter" nevertheless, when BCP is activated/deactivated for that unavailability the Explanation field is empty. We would need to apply the same approach in all the cases. When generating the notification for the BCP, if the explanation is empty , it will be substituted with "No explanation provided by the reporter". No workaround. | DG TAXUD | MON | IM853695 | 22/05/2025 | 04/12/2025 | 16/12/2025 | MON 3.1.1.0 | ICS2-12711 | Yes | Medium | Low
133 | KE25481 | In Create ENS Filing module for the field group 'Packaging', the field 'Type of packages' does not get cleared when a user adds a new item to the list. This will be fixed and the data element will be empty for the new line to be filled in. Until this is fixed, the value appearing has to be ignored/replaced with the needed value from the drop-down code list. No workaround. | DG TAXUD | STP | IM848827 | 12/5/2025 | In conformance | In production | STP 3.1.0.0 | ICS2-12660 | Yes | Low | Low
135 | KE25488 | It was discovered that the search of messages in ICS2 STP UI is performed in the UTC timezone instead of the timezone of the local of the server. This leads to messages submitted between 00:00 - 02:00 CEST not being returned in the search results. Workaround: The EO's can set the To Message Timestamp field in the Search Messages page of ICS2 STP to +1 day from the date of submission to receive results for Messages submitted between 00:00 - 02:00 CEST. | DE EO | STP | IM850755 | 15/05/2025 | In conformance | In production | STP 3.1.1.0 | ICS2-12774 | Yes | Medium | Low
137 | KE25526 | Upon investigating the IM835741 ICS2-12421, a system misbehavior was identified caused by an ineffective query, specifically an unnecessary inner join to the RISK_ANALYSIS table during the linking process. As a result, the system cannot link the F43/F44 to the master filing until the Full RA is triggered for the ENS and the related database table is populated with the record. This issue is limited to the configured wait time before the asynchronous Full RA triggering and occurs only if an RA for the master filing has not yet been triggered. CR will be updated to remove the unnecessary inner join to the RISK_ANALYSIS table during the linking process, particularly from the linking query of F43 and F44. This adjustment will allow successful linking of F43 and F44 to the master filing, even if the default wait time for asynchronous Full RA triggering has not expired yet. Workaround: Regarding the possibility for successful completion of "F42 Controls and Arrival Notification" self-conformance test scenario a workaround has been applied and it can be completed by the economic operators executing it. | DK EO | CR | IM835741 | 10/04/2025 | In conformance since 08/12/2025 | In production since 10/12/2025 | 3.1.1.1.0 HF | ICS2-12732 | Yes | High | High
138 | KE25527 | The "Additional information" class under the master consignment level in the STP UI initially (when the field is considered 'clean', i.e. the user has not interacted with the field) appears as mandatory. Upon first interaction with the field (i.e. the user adds an 'Additional information' and then deletes its) the application handles the field as optional (which is the intended behavior), allowing the user to proceed with their submission. Workaround: The field can be added and removed and then the submission of the ENS filing can be processed successfully without the field being treated as mandatory. | ES | STP | IM866540 | 18/06/2025 | In conformance | In production | 3.1.0.0 | ICS2-11721 | Yes | Medium | Low
139 | KE25528 | IE3N07 "House consignment in incorrect state notification" error description for the incorrect state of the house consignment contains "ENS filing in a wrong state." instead of "House consignment in a wrong state". This has to be fixed for clarity reasons. No workaround. | DE EO | CR | IM864592 | 13/06/2025 | Q3/2026 | Q3/2026 | 3.2.0.0 | ICS2-12930 | Yes | Low | Low
140 | KE25532 | Currently it is not possible to amend ENS filings submitted more than 30 days ago - neither via the "Create ENS filing"/Amend nor via the "Upload several ENS filings" functionality. It is decided that it should be possible via "Upload several ENS filings". No workaround. | PT EO | STP | IM824694 | 13/03/2025 | In conformance | In production | 3.1.1.0 | ICS2-12953 | Yes | Medium | Low
141 | KE25534 | It is possible in rare cases that IE3R01/IE4R01 message reaches the system simultaneously with IE3N03/IE4N04, causing IE3N03 to be routed to the delay path instead of being sent to TAPAS. For this reason the common query between the two corners have to be updated in order to lock the same row and the commits to be applied sequentially. No workaround. | LU EO | STI | IM826068 | 17/03/2025 | In conformance | In production | 3.1.0.1 Hotfix | ICS2-12242 | Yes | Medium | Low
142 | KE25539 | During the execution of scenarios part of the EO self-conformance the LRN of the submitted ENS filings must not contain "_". Otherwise, the succesful completion of the scenario is not possible. | DK EO | EO Self-conformance | IM871808 IM767084 | 27/06/2025 06/11/2024 | In conformance | In production | 3.1.0.0 | ICS2-11283 | Yes | Medium | Low
144 | KE25555 | In Business Role and Campaign Status dropdowns of the EO Self Conformance Campaign tab , there are some values (e.g Postal Operator) that cannot be translated even if the key is present in TATAFNG. This is due to the key ics2.test-campaigns_enum_business-role_postal_operator having an underscore between postal and operator. No workaround. | FI | MON CONF | IM852915 | 20/05/2025 | 04/12/2025 | N/A, only for conformance | 3.1.1.0 | ICS2-13053 | Yes | Low | Low
145 | KE25601 | According to the specs from CFSS the field ‘Container identification number’ has the length an..17. That is reflected in the UI. For some ENS Filing (such as IE3F10) the field ‘Container identification number’ has the business rule R3021 attached. R3021 states: The format of this attribute is ZZZZ9999999 (ISO 6346). That is where the 11 character limitation stems from. No workaround. General comment - the error handling and visualization in the STP is currently being enhanced with better error visualization and guidance to the user. | DG TAXUD | STP | IM877222 | 10/07/2025 | Cancelled | Cancelled | Cancelled | ICS2-13058 | Yes | Low | Low
147 | KE25676 | During the execution of the "Controls and AN" scenarios for the EO Self-conformance for F20 and F27 there is an issue preventing the successful completion of the scenarios - the NES mock-up cannot process ENS filings types F20 and F27 which contain "Transport equipment" data class on master consignment goods item level for the generation of the related IE3N09/IE4N11 AEO Control notification. Workaround: The submitted F20/F27 by the EO during the testing should not include "Transport equipment" data class on master consignment goods item level. | EO | CR EO Self-conformance | IM890934 | 12/08/2025 | In conformance since 08/12/2025 | N/A, only for conformance | 3.1.1.1.0 HF | ICS2-12110 | Yes | Medium | Low
148 | KE25680 | It was identified in the STP that the sub-tabs are not turning red when a mandatory data element/data class is not filled in. The issue is the incomplete implementation of the tab-level validation logic within the user interface. Specifically, the system does not correctly evaluate whether mandatory sections such as the Goods Items tab have been filled in. As a result, tabs remain visually marked as valid (blue) even when required data is missing. No workaround. General comment - the error handling and visualization in the STP is currently being enhanced with better error visualization and guidance to the user. | LV | STP | IM892778 | 20/08/2025 | Q3/2026 | Q3/2026 | 3.2.0.0 | ICS2-13325 | Yes | Medium | Low
149 |  | There was a high number of incidents registered via CSD and NSD for many ENS filings rejected due to not satisfactory data quality. The root cause was the configuration of stop words for the goods description on the central repository side. The stop words will remain configured and further upgraded. At the same time it was identified that a whitelist of words/expressions has also to be considered. The whitelist will be composed of phrases (very often a combination of stop words) which are considered as valid goods description. For example, the phrase “Vehicle registration plates” is composed of stop words but the combination of those is a valid goods description. The whitelist will be configured on the common repository and aim to avoid the unnecessary rejection of ENS filing. | NL | CR | IM828001 | 21/03/2025 | Q3/2026 | Q3/2026 | 3.2.0.0 | ICS2-12630 ICS2-12631 | Yes | High | Medium
150 |  | Currently, the invalidation request is processed based on the IE3Q04/"Document issue date". If this timestamp is before the registration timestamp of the related ENS filing, then the subsequent processes are not stopped and the subsequent/ongoing processing of the invalidated ENS filing continues. Therefore, assessment complete notification can be sent for invalidated ENS filings. For the invalidation of the ENS filing the timestamp when the invalidation request is received has to be used instead. No workaround. | HR | CR | IM809992 | 13/02/2025 | In conformance since 08/12/2025 | In production since 10/12/2025 | 3.1.1.1.0 HF | ICS2-12344 | Yes | Medium | Low
151 | KE25699 | When F10 is filled in based on uploaded .json, it has to be ensured that the "Container indicator" field is switched on and off in order to have the field populated with either 0/1 value instead of null. The "Container indicator" may not be properly populated from the uploaded template due to different reasons. With the fix to be deployed, the null value will be transformed to 0 and there will be no issue. Workaround: Once the content of F10 is populated, the user has to switch on/off manually the "Container indicator" and leave the needed value at the end. Then the ENS filing can be submitted successfully. General comment - the error handling and visualization in the STP is currently being enhanced with better error visualization and guidance to the user. | LV | STP | IM893576 | 22/08/2025 | Q3/2026 | Q3/2026 | 3.2.0.0 | ICS2-13369 | Yes | Medium | Low
152 | KE25715 | For ENS filings that include the field 'Estimated Date and Time of Departure' and implement the rule R3053, it was discovered that the implementation of the rule R3053 contains an error. Based on the rule The 'Estimated date and time of arrival' cannot be earlier than the 'Actual date and time of departure' or 'Estimated date and time of departure', we limit the dates of field 'Estimated date and time of arrival' so they cannot be an earlier time than 'Actual date and time of departure' or 'Estimated date and time of departure'. We also apply the rule 'in reverse', limiting the date on 'Actual date and time of departure' or 'Estimated date and time of departure' so that it cannot be later than 'Estimated date and time of arrival', if that field was filled first. The second case is the root of the issue. For the field 'Estimated date and time of departure' the maxDate property, which is in charge of enforcing the functionality described above, is set to monitor the value of the 'Estimated date and time of departure' field (itself) instead of the 'Estimated date and time of arrival'. This is the reason each time a date is inputed in the field it becomes the new max date allowed. This fix will ensure accurate date relationships across the form and prevent invalid date selections. General comment - the error handling and visualization in the STP is currently being enhanced with better error visualization and guidance to the user. | DG TAXUD | STP | IM898662 | 09/09/2025 | Q3/2026 | Q3/2026 | 3.2.0.0 | ICS2-13419 | Yes | Medium | Low
153 | KE25786 | Investigation of IM899137 found that a NullPointerException is thrown during the F16 invalidation process. The exception occurs when the F16 link ID is null in the database because the previously linked F14 filing was invalidated. The invalidation process of F14 sets the link id of the F16 that was linked to it to null in order to make it eligible to be linked with new F14 if it is required. The current F16 invalidation logic does not handle this null condition. This issue is isolated to the F16 invalidation workflow, all other workflows remain unaffected. As a result, the F16 cannot be invalidated, and theinvalidation process terminates. To resolve this, CR will be updated to correctly handle the null link ID during F16 invalidation. When the link id is absent due to prior F14 invalidation, the logic will treat this as an expected condition and proceed with the workflow, allowing the F16 invalidation to complete. A script was provided to correct the link ID and reprocess the invalidation request whenever the issue occurs again until the deployment of the fix. | DE | CR | IM899137 | 10/09/2025 | Q3/2026 | Q3/2026 | 3.2.0.0 | ICS2-13535 | Yes | Medium | Low
154 | KE25795 | It was reported by several economic operators that for F21 no assessment complete notification was received. After deeper investigation it was identified that the created ENS is huge (bigger than 20MB's) and its processing on the common repository side is blocked. Therefore, no risk analysis has been triggered (respectively no assessment complete notification is generated). The problem is currently under further investigations. Currently there are 3000 ENS's blocked. Investigation is ongoing for their further processing. No workaround. | EO | CR | IM907220 IM914696 | 04/10/2025 | TBC | TBC | TBC | ICS2-13585 | Yes | High | High
155 | KE25804 | When editing an existing Transport Equipment entry, the Seal Identifier field becomes incorrectly disabled, preventing users from adding new values to the seal array. Workaround As a temporary workaround, users can modify the Number of Seals field. This triggers and re-enables the Seal Identifier field, allowing input as expected. | DG TAXUD | STP | IM909354 | 10/10/2025 | Q3/2026 | Q3/2026 | 3.2.0.0 | ICS2-13604 | Yes | Medium | Low
156 | KE25805 | Currently in the STP UI when data should be declared following the pattern defined in rules and conditions the correctness of the data are checked in UI and user is provided with the information on correct patter to be used e.g. Communication - Identifier, Transport equipment - Container identification number etc. Nevertheless, in case of Goods items - CUS code this approach is not followed meaning, if users provide incorrect CUS code format in the error message it is informed that the format is not correct but the error message do not provide information what is the expected format as per R3020. Please align the error message for CUS code with other error messages by indicating the expected format "9999999-9". No workaround. General comment - the error handling and visualization in the STP is currently being enhanced with better error visualization and guidance to the user. | DG TAXUD | STP | IM909744 | 13/10/2025 | Q3/2026 | Q3/2026 | 3.2.0.0 | ICS2-13609 | Yes | Medium | Low
157 | KE25806 | In CFSS there are two similar conditions - C3013 (Master level) and C3014 (House level). C3013 is correctly implemented in STP UI meaning if the Goods transported in container switch is turned ON Add icon is activated both for Transport Equipment on Master level and Transport Equipment on Master Level -> Goods Item level and vice versa if switch is switched OFF Add button is disabled for Transport Equipment on Master level and Transport Equipment on Master Level -> Goods Item level. Nevertheless, C3014 is implemented just partially - if the Goods transported in container switch is turned ON/OFF Add icon is activated/deactivated just for Transport Equipment on House level. For Transport Equipment on House Level -> Goods Item level is always active no matter whether Goods transported in container switch is turned ON or OFF which is not the expected behaviour of UI and C3014. As per C3014 Transport equipment should not be used if Goods transported in container switch is turned OFF. No workaround. (not blocking) | DG TAXUD | STP | IM910984 | 16/10/2025 | Q3/2026 | Q3/2026 | 3.2.0.0 | ICS2-13646 | Yes | Medium | Low
158 | KE25818 | It was detected that F30, F32, F34 containing more than 1000 house consignments cannot be processed. Workaround: ENS filings to contain less house consignments until the issue is fixed. | IE | CR | IM910872 | 16/10/2025 | 13/01/2026 | 15/01/2026 | 3.1.2.0 HF | ICS2-13674 | Yes | High | High
159 |  | There was a huge amount of F34's v2 blocked - ENS filings registered with MRN generated and communicated via IE3R01 ENS Registration response but the processing cannot continue as there is no "Estimated date and time of arrival". With v3 of F34 this data element is mandatory. Once the issue is fixed, the blocked ENS filings will be re-processed. Workaround: Even if "Estimated date and time of arrival" is optional, to be provided by the economic operator. After the issue is fixed in 3.1.2.0 then F34 v2 even without "Estimated date and time of arrival" will be possible to be processed. | DG TAXUD | CR | IM908455 | 08/10/2025 | 13/01/2026 | 15/01/2026 | 3.1.2.0 HF | ICS2-13729 | Yes | High | High
161 |  | There was a question raised by an economic operator if the entities from F13 and F17 related to the same ENS are linked. In case F13 and F17 are submitted in different namespace versions, the goods shipment information from F17 is not linked to the corresponding house consignment in F13. Until v2 of F13 and F17 is decommissioned from production (and conformance) - planned for February 3rd 2026 - the entities from F13 and F17 with different namespace versions are not linked. The ENS created is based only on F13 and the goods shipment information is missing in the ENS. In STP already v3 of both F13 and F17 is available. No workaround. | EO | CR | IM917387 | 06/11/2025 | N/A | N/A | N/A | N/A | Yes | Medium | Medium
163 | KE25861 | It is possible to amend the house transport document in F50 in STP UI. Only upon submission of the ENS filing amendment, there is an ENS lifecycle validation error notification generated (IE3N01). | DG TAXUD | STP | IM919752 | 13/11/2025 | TBC | TBC | TBC | ICS2-13886 | Yes | Low | Low
Note on K1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For internal purposes.

## RfC's
RfC Identifier | RfC Name | MS CAB | Planned implementation date in conformance (the indicated timing can vary and will be updated in case of a change) | Planned implementation date in production (the indicated timing can vary and will be updated in case of a change) | Software release version | EO Impact
RfC220006 | R2 - ENS Consultation per receptacles | MS CAB9, 27/04/2023 | In conformance | In production | 3.1.0.0 | Yes
RfC220007 | R2 - Air - Notifications to be added for F25 | MS CAB9, 27/04/2023 | N/A | In production |  | Yes
RfC230001 | R3 - Rail - New ENS filing type F52 for partial master information | MS CAB9, 27/04/2023 | Q4/2026 | Q4/2026 | 3.3.0.0 | Yes
RfC230002 | R3 - Rail - New ENS filing type F53 for house level information | MS CAB9, 27/04/2023 | Q4/2026 | Q4/2026 | 3.3.0.0 | Yes
RfC230003 | R3 - Rail - New ENS filing type F54 for partial house level information | MS CAB9, 27/04/2023 | Q4/2026 | Q4/2026 | 3.3.0.0 | Yes
RfC230004 | R3 - Rail - New ENS filing type F55 for goods shipment information | MS CAB9, 27/04/2023 | Q4/2026 | Q4/2026 | 3.3.0.0 | Yes
RfC230005 | R3 - Make active border transport means amendable for rail and road | MS CAB10, 22/11/2023 | In conformance | In production | 3.1.0.0 | Yes
RfC240004 | Road - New ENS filing type F56 master information | MS CAB11, 01/10/2024 | Q4/2026 | Q4/2026 | 3.3.0.0 | Yes
RfC240005 | Road - New ENS filing type F57 for house level information | MS CAB11, 01/10/2024 | Q4/2026 | Q4/2026 | 3.3.0.0 | Yes
RfC240006 | Road - New ENS filing type F58 for partial house level info | MS CAB11, 01/10/2024 | Q4/2026 | Q4/2026 | 3.3.0.0 | Yes
RfC240007 | Road - New ENS filing type F59 for goods shipment info | MS CAB11, 01/10/2024 | Q4/2026 | Q4/2026 | 3.3.0.0 | Yes